United Nations

Development Assistance Framework (UNDAF)

for Lesotho

2002 - 2007

TABLE OF CONTENTS

SECTION I: THE UNDAF PREPARATION PROCESS	1

I.1	Introduction	1

I.2	Rationale	1

I.3	CCA/UNDAF Preparation Process in Lesotho	1

I.4	Lessons Learned in the CCA/UNDAF Preparatory Process	2

SECTION II: DEVELOPMENT CHALLENGES IN LESOTHO	4

II.1	Lesotho’s National Development Goals	4

II.2	National Development Strategies	6

II.3	Progress Made on National Follow Up to Global Conferences and Declarations	7

SECTION III: United Nations Co-ordinated Response and Co-operation Strategies	9

III.1	Purpose of the UNDAF	9

III.2	The Mission of the United Nations in Lesotho	9

III.3	Lessons learned from past United Nations Development Assistance	10

III.4	The Strategic Focus of the UNDAF	11

III.5	UN System Strategic Objectives under the First UNDAF	12

SECTION IV: FOLLOW Up and REVIEW	25

IV.1	Implementation Arrangements	25

IV.2	The Resident Co-ordinator System in Lesotho	25

IV.3	UN Inter-Agency Theme Groups	26

IV.4	Expected Use of UNDAF for Advocacy, Policy Dialogue and Aid Coordination	28

IV.5	Institutional  Arrangements & Commitments	28

IV.6	Strengthening Development Partnerships	28

IV.7	Monitoring and Evaluation Plan	29

SECTION V: RESOURCE USE	31

V.1	The Common Resources Framework	31

SECTION VI: ANNEXES	34

VI.1	Lesotho’s UNDAF Work Plan	34

VI.2	Lesotho Development Indicator Tables	36

LESOTHO united nations DEVELOPMENT ASSISTANCE FRAMEWORK

We, the United Nations Country Management Team in Lesotho, pledge our commitment to utilising the UNDAF to heighten inter-agency co-ordination and cooperation, with the overarching intention of enhancing the impact of our assistance to the Government of Lesotho. The UNDAF document has been prepared with the full involvement of all the UN Agencies, funds and programmes represented below, and was formulated in accordance with our respective mandates and objectives.

____________________

FAO Representative

Dr. Admir P. M. Bay

____________________

World Bank Representative

Mr. Fayez Sadek Omar

___________________

UNHCR Regional Programme Advisor

Mr. Biong Deng

___________________

UNICEF Representative

Ms. Kimberly Gamble-Payne

___________________

UNIDO Representative

Mr. Niels Biering

____________________

WHO Representative

Dr. Ruth Tshabalala

____________________

WFP Representative

Mr. Igor Marincek

____________________

UN Resident Coordinator, and representing UNDP, UNFPA and UNIC

Mr. Edward Omotoso

LIST OF acRONYMS

AIDS		Acquired Immune Deficiency Syndrome

BOS		Bureau of Statistics

BWI		Bretton Woods Institutions

CCA		Common Country Assessment

CEDAW	Convention on the Elimination of all Discrimination against Women

CPC		Country Programme Committee

ECD		Early Childhood Development

ECDC		Early Childhood Development Center

ECOSOC	Economic and Social Council

EIA		Environmental Impacts Assessment

EU		European Union

FAO		Food and Agricultural Organisation

FPE		Free Primary Education

GDP		Gross Domestic Product

GIS		Geographic Information System

GNP		Gross National Product

HIV		Human Immunodeficiency Virus

IBRD		International Bank for Reconstruction and Development

IFAD		International Fund for Agricultural Development

IOM		International Organisation of Migration

IMF		International Monetary Fund

IMR		Infant Mortality Rate

LCD		Least Developed Country

LHRF		Lesotho Highlands Revenue Fund

LHWP		Lesotho Highlands Water Project

MDP		Ministry of Development Planning

MoE		Ministry of Education

MOHSW	Ministry of Health and Social Welfare

NAPCP	National AIDS Prevention Programme

NDP		National Development Plan

NEAP		National Environment Action Plan

NEX		National Execution

NFE		Non-formal Education

NGO		Non-governmental Organisation

NHDR		National Human Development Report

ODA		Official Development Assistance

ODA		Overseas Development Agency

OECD		Organisation for Economic Cooperation and Development

PHC		Primary Health Care

PLWHA	People living with HIV / AIDS

PRSP		Poverty Reduction Strategy Paper

PSIP		Public Sector Investment Programme

RC		Resident Co-ordinator

RTC		Round Table Conference

SADC		Southern African Development Community

SME		Small and Medium Enterprises

SIDA		Swedish International Development Agency

STD		Sexually Transmitted Disease

STI		Sexually Transmitted Illness

TEBP		Targeted Equity Based Programme

TOR		Terms of Reference

TVET		Technical and Vocational Education and Training

UN		United Nations

UNAIDS	Joint United Nations Programme on HIV/AIDS

UNCT		United Nations Country Team

UNDAF 	United Nations Development Assistance Framework

UNDG		United Nations Development Group

UNDP		United Nations Development Programme

UNESCO	United Nations Educational, Scientific and Cultural Organisation

UNFPA	United Nations Population Fund

UNHCHR	United Nations High Commissioner for Human Rights

UNHCR	United Nations High Commissioner for Refugees

UNIC		United Nations Information Centre

UNICEF	United Nations Children's Fund

UNIDO	United Nations Industrial Development Organisation

UNIFEM	United Nations Development Fund for Women

UNODCCP	United Nations Office for Drug Control and Crime Prevention

UNITeS	United Nations Information Technology Services

UNTWG	United Nations Technical Working Group

USD 		US Dollars

WB 		World Bank

WFP		World Food Programme

WHO		World Health Organisation

# SECTION I: THE UNDAF PREPARATION PROCESS

### I.1	Introduction

In 1997 the United Nations Secretary-General, proposed a series of reforms to enhance the impact of UN development assistance in the 21st century. To achieve this objective, the United Nations Development Assistance Framework (UNDAF) as the centrepiece of United Nations development cooperation at the country level, serving as a planning framework for all UN Development Funds, Programmes and Agencies that reflect common programme areas  that respond to national development priorities and needs. In his report on UN reform, the Secretary-General stated that: "In order to achieve goal oriented collaboration, coherence and mutual reinforcement, the United Nations programmes of assistance will be formulated and presented as a single United Nations Development Assistance Framework with common objectives and time-frame." .

The UNDAF process is preceded by the formulation of a national Common Country Assessment (CCA). As a analysis of the development situation of the country concerned, the CCA lays the foundation for the formulation of the UNDAF at country level. Through a consultative process, the CCA assesses the extent to which progress has been made against the Global UN Conferences and Conventions, and the associated International Development Targets. The assessment is based on an extensive review of the political, economic, social and human rights developments.

### I.2	Rationale

Building on the analysis of the CCA, the UNDAF defines common UN positions on key development issues and outlines the strategies that will be used to support the Government of Lesotho within programming framework characterised by increased collaboration among UN Agencies. The strategies outlined in the UNDAF will ensure that National Priorities are pursued in the context of the global goals and objectives as agreed to at the various UN Conferences and Conventions. The fundamental objective of the UNDAF is to increase the impact of the UN System’s assistance to the Government of Lesotho  through increased co-ordination and coherent programming.

Through the CCA process, six distinct issues emerged that were found to be particularly pressing in addressing the development situation in Lesotho. These six areas were identified as: poverty reduction within a context of good governance; the fight against HIV/AIDS; promoting the rights of children and youths; ensuring food security and natural resource management., and; meeting the global and regional challenges facing Lesotho.

These are also areas in which the UN Agencies possess significant experience and leverage, and where a united UN Country Team should have the greatest impact. It  has therefore been  agreed that targeted assistance to these areas would complement the Government of Lesotho’s development priorities and strategies.

### I.3	CCA/UNDAF Preparation Process in Lesotho

Responding to the aims of General Assembly Resolutions 47/199, 50/120 and 50/227, the CCA/UNDAF process will increasingly foster more effective collaboration among development partners at the country level and within the UN System. The UNDAF is to be the centrepiece of UN development assistance to Lesotho, and lays the foundation for enhanced cooperation between the UN System, the Government of Lesotho, and other development partners. Lesotho is in the second group of countries to implement the CCA/UNDAF processes.  The main mechanisms for the preparation of the CCA were the UN Theme Groups. A Task Force comprising all UN Agencies was formed to spearhead the co-ordination of information and drafting of the CCA. The UN System and government departments provided the data for various indicators drawing predominately upon official data and research made available through the Bureau of Statistics and line ministries.. A common database for Lesotho’s development indicators has been developed. This facility will provide the indicator framework needed to monitor progress under various UN conference goals.

The CCA Task Force transformed itself into the UNDAF Task Force in July 2000 to co-ordinate the formulation of the Lesotho's first UNDAF. Members of the Task Force act as UNDAF focal points in their respective Agencies and ensures that Agency colleagues are kept informed of progress and are actively involved in the process.

### I.4	Lessons Learned in the CCA/UNDAF Preparatory Process

Lesson 1:	The CCA/UNDAF process requires the full commitment and participation of every UN agency. The very nature of the CCA/UNDAF process made the full involvement of every UN agency in Lesotho of the utmost importance, as the UNDAF is to reflect the purpose and identity of all agencies in the country.  The UN inter-agency Theme Groups proved to be particularly useful for information sharing and the development of inter-agency solidarity. However, this is very much a learning process, and continued efforts are needed to institutionalise the work of the Theme Groups.

Lesson 2: 	Broad and extensive consultation is paramount. The preparation period, therefore, involved extensive and broad consultation, with Government, development partners and representatives from civil society. This extensive consultation proved to be paramount in the successful formulation of the UNDAF.

Lesson 3: 	A successful CCA/UNDAF process requires full Government ownership. The Government of Lesotho was involved as extensively as possible throughout the CCA/UNDAF process to ensure that the objectives of the UNDAF would be in full support of national goals and priorities.  A Government official from the Ministry of Development Planning is a full member of the UNDAF Task Force. The March 2000 CCA consultation with Government proved to be particularly useful in this regard, as did the full participation of a Government of Lesotho representative in the UNDAF Task Force.

Lesson 4:	A hands-on approach in the preparation and drafting of the CCA/UNDAF directly by the UN staff increases ownership and foster a common understanding of a country’s development opportunities and challenges. The hands-on approach  increases synergy and interactions among UN staff.  It helps improve understanding of individual agency mandates reduces inter-agency rivalries.

Lesson 5:	The CCA/UNDAF process has to be treated as one continuous processes within the UN family and particularly to other development partners outside the UN System.

Lesson 6: 	There is need for joint partnerships to generate research and data, for the CCA/UNDAF process to be successful. A  sustainable information base, including reliable indicators, is indispensable. Such a database should be created in collaboration with the Government, to foster ownership of the process,  UN Agencies’ involvement is mandatory.

# SECTION II: DEVELOPMENT CHALLENGES IN LESOTHO

### II.1	Lesotho’s National Development Goals

Lesotho's national development goals  and overall economic growth strategies have undergone series of transformations and structural changes in the last two decades all aimed at poverty eradication, attaining self-sufficiency and creating prosperity for Lesotho’s citizens by the year 2000 and beyond.

The 1996,  Pathway Out of Poverty report was the first landmark document focussing on poverty reduction. The report was prepared in collaboration with Government, the Lesotho Council of NGOs and donors. The report has explored the incidence of poverty in Lesotho, its geographical distribution, and forwarded practical priority policy change necessary to reduce poverty.

This report was followed in 1997, by the Strategic Economic Options Study which specifically targeted  on improved performance of all sectors of the economy. The Report examined a number of strategic options that could be considered in addressing and dealing with the critical issues limiting economic development in Lesotho.

In terms of overall economic developments, Lesotho has performed remarkably well in the past two decades.  Real growth in Gross Domestic Product (GDP) averaged 4.2 percent in the period 1980 to 1989.  During the period 1990 – 1997 GDP growth rates accelerated to 5.2 percent placing Lesotho among the top ten fastest growing economics in Sub-Saharan African countries.  Growth in the late 1980’s and early 1990’s was fuelled by expansion in manufacturing, construction, services and general improvement in fiscal performance through IMF supported structural adjustment programmes launched in 1988.

The single major contribution to Lesotho’s growth has been the construction                                         sector, specifically the Lesotho Highlands Water Project (LHWP) which is the largest water development project in Africa.  The country is earning substantial royalties from the sale of water to the neighbouring Republic of South Africa, which is a major contributor to the economy.

Recently the country has experienced major reversals in macro-economic gains. The scaling down of the Lesotho Highlands Water Project (LHWP) (as phase one was being completed) contributed to the poor performance as a result of the progressive decline in capital inflows for construction of the dam and related infrastructure.

The political crisis of 1998, has had a more sudden impact in its contribution to macro-economic reversals. Continued civil unrest following the elections of May 1998 caused involuntary work stoppages and disrupted national production.  Political tensions mounted in September 1998 resulting in the SADC military intervention. The ruling Lesotho Congress for Democracy won 79 of the 80 parliamentary seats.  Although the elections were certified free and fair and as meeting the best standards by the international observers, opposition parties refused to accept the election results. Most of the commercial retail and manufacturing base of the country in the major urban centres of Maseru, Mafeteng and Mohale’s Hoek, were destroyed and national production output was brought to an abrupt end and GDP dropped by 5.5 per cent. About 400 private businesses were shut down, and an estimated 6000 jobs lost.  A Post-conflict Needs Assessment conducted by a UNDP/World Bank Team estimated total loss to be about US$60 million.

The country has further suffered adverse  impacts from the world gold crisis experienced in 1999 which affected South Africa gold mining industry, on which the economy of Lesotho is heavily dependant.  A large proportion of Basotho migrant workers are employed in South African gold mines and their remittances have declined in real terms indicated by the below GDP growth rates of Gross National Income (GNI) in recent years. In 1994 migrant remittances accounted for 31 per cent of GNP, in 1998 this had declined to 23per cent. As proportion of GDP the decline ranges from 44 per cent in 1994 to 31 per cent in 1998.

Lesotho’s employment situation has worsened as a direct consequence of the mine closures, as well as mechanisation of the mines and pressure to give priority to South African nationals.    In the past decade South Africa employed an average of 125,000 Basotho nearly 50 per cent of the male labour force.  In the first half of 1999 the figure went down by 50 per cent to 65,000.  The latest estimates of total unemployment range between 23 per cent and 34 per cent.  The Government of Lesotho has been grappling with the growing problem of unemployment, which has been progressively worsening  since 1986.  High economic growth rates during the period have not translated into corresponding growth rates of employment.  The economy has generally failed to transform gains from stabilisation into productive and labour intensive investments.  This has happened in the face of a rapidly growing labour force with new entrants not being absorbed.  The Ministry of Employment and Labour estimates that 25,000 youths enter the work force every year but only 9,000 find employment.

Poverty is accelerating in Lesotho, hence the 8th Round Table Conference held in Geneva in 1997 focused on Poverty Reduction.  It is estimated that over 50% of the population is living below the poverty line.  In 1993 just under half of the population lived in poverty (with consumption levels of less than half the national average) and about one quarter is characterised as extremely poor.

The progress in improving longevity in Lesotho has been remarkable.  However, prevalence of the HIV/AIDS virus threatens to reverse one of the most critical indicators of human development.  The World Bank estimates that the presence of AIDS in Lesotho will reduce the average real GDP growth rate during the period 1986-2015 from 4.4 percent without AIDS to 3.6 percent with AIDS.   Access to health facilities has improved since the country’s adoption of Primary Health Care programme.  However, the poor located in remote locations cannot access basis health care.  Population/doctor/nurse ratios remain large and most health care institutions are understaffed and need modern equipment.  Improved access to primary education has received a big boost with the Government’s adoption of the Free Primary Education in 2000.   Particular attention will have to be paid to reversing the high drop out rates and improving overall quality of education.

Agricultural production and productivity are on the decline.  The main contributing factor being severe environmental degradation and loss of arable land.  Recent adverse El Nino related weather phenomenon have worsened the situation, resulting in periodic drought spells affecting over 83% of the population which is dependant on rain fed agriculture.  Recent assessments have shown that poverty is most severe within rural households.

The prevailing political situation has  not  been conducive to foreign investment.  It is estimated that net private investment inflows dropped by 50% in 1998 compared to 1997, mainly due to reduced investor confidence following the civil unrest. Government has made a lot of effort to improve the economy through both public sector and economic reforms, and is now seriously engaged in political reforms.  The Interim Political Authority (IPA) created in 1998 by an Act of Parliament comprises  all political parties. It is the main body charged with the responsibility  to steer the political dialogue towards consensus on a number of political issues, particularly the holding of new elections.  Initial  timeframes for holding the elections by May 2000 has elapsed.  The setting of a new schedule for the next election is part of the ongoing political dialogue.

### II.2	National Development Strategies

Given the enormous development challenges in Lesotho, the Government adopted poverty alleviation as its highest priority.  The Sixth National Development Plan (6th NDP 1996/97 – 1998/99) was formulated adopting the principle of Sustainable Human Development focusing on:

- Rapid economic growth, the priority being improvement in the quality of economic management (civil service reforms and restructuring of parastatals);

- Improvement in public investment policies and an enhanced role of the private sector;

- Enhanced environmental management, drought mitigation and improvements in agricultural productivity;

- Rapid growth of employment and income generating opportunities and equitable distribution of income; and;

- Improvement in health delivery and education services.

To achieve the national development objectives stated above, Government recognised that it had to translate the successes of the macro-economic reforms into poverty reduction and employment generation measures in a more targeted approach.

The Government of Lesotho is currently completing the Seventh National Development Plan covering the period 1999/00 – 2001/02, outlining short- and medium-term sectoral policies, targets and strategies. Moreover, the Government has embarked on a process of preparing a Poverty Reduction Strategy Paper (PRSP) to be completed through comprehensive consultations in 2002. Simultaneously, a more long-term vision for  Lesotho is being developed to guide national policy formulation and implementation into the year 2020. Although the process is still in its initial stages, the Government of Lesotho has defined those challenges that potentially pose the greatest threat to Lesotho’s development in the next 20 years, and have thus identified focus areas of national priority. The Government intends to use the Vision 2020 Framework to build on those gains already made through the short to medium-term National Development Plan framework.

Lesotho’s Vision 2020 Framework identifies several critical strategies required for the ultimate attainment of the national long-term goals, and the realisation of their vision statement that “By 2020, Lesotho shall be a stable democracy, united, prosperous nation at peace with itself and it’s neighbours. It shall have a healthy and well-developed human resource base. Its economy will be strong, its environment well managed and its technology well-established”. The main elements are outline below.

Employment Creation through:

- use of labour intensive methods;

- sustainable employment schemes and programmes;

- promotion of  rural development opportunities, and;

- establishment of Small and Medium Enterprises.

Sustainable Human Capacity Enhancement through:

- appropriate education and training that is accessible to all;

- quality health services that are accessible to all, and;

- the control of HIV/AIDS using a national, multi-sectoral response.

Sustainable Development, Growth and Prosperity to all through:

- the development of an aggressive programme of entrepreneurship at all levels of the economy;

- the intensification and diversification of agricultural production;

- cost-effective utilisation of  local materials and resources for industrial development;

- aggressive environmental management practices, and;

- development and promotion of  the Tourism Industry.

Reform/Democratisation/Empowerment through:

- the reform of the chieftainship institutions to align them with the democratic dispensation and modern institutions;

- resuscitation and strengthening of  law enforcement structures;

- the acceleration of  the implementation of local government;

- establishment of  social, cultural, religious and political tolerance amongst all citizens, and;

- enhancement of  patriotism and its values at all levels of society.

In addition to the delineation of the above critical goals, the Vision 2020 Framework identifies other potential focus areas as windows of opportunity to address national challenges and promote sustainable development at both policy and programmatic levels.  At a policy level, the implications of the recent political and socio-economic trends, dictated a shift in UN assistance to support the country’s efforts to restore stability in the aftermath of the 1998 conflict. The UNCT interventions have centred around facilitation of political dialogue and providing catalytic technical and advisory services.  The UN Resident Coordinator is co-witness on behalf of the United Nations to the December 1999 Agreement reached between the Government of Lesotho and the Interim Political Authority. Post conflict/conflict prevention and facilitating national dialogue will be a strategic area of intervention in the forthcoming UN Agencies’ country programmes.

The UNCT in Lesotho is in full agreement that the thematic areas emerging from the Vision 2020, PRSP, National Development Plan and the CCA processes require prioritisation through collaborative and coherent development programming. The common UNDAF programming framework, outlining UN strategic objectives and areas of targeted assistance will support the Government to the fullest extent possible in its pursuit of its national objectives. Section III of the UNDAF describes the way in which the UNCT intends to approach its collaboration with Government in the pursuit of Lesotho’s development goals. Several strategic objectives have been identified in response to specific development challenges.

### II.3	Progress Made on National Follow Up to Global Conferences and Declarations

Integrated implementation of follow-up to global UN Conferences remains a challenge in Lesotho, due mainly to the political, economic and managerial situation in the country. However, over the years, Lesotho has streamlined its national legislation and programmes to meet the requirements put forth by global conferences and declarations listed below and some encouraging improvements can be discerned.

1978 	International Conference on Primary Health Care  – Alma Ata

1990 	World Summit for Children – New York

1990 	World Conference on Education for All – Jomtien

1992 	United Nations Conference on Environment and Development – Rio de Janeiro

1993	World Conference on Human Rights – Vienna

1994	International Conference on Population and Development – Cairo

1995	World Summit for Social Development – Copenhagen

1995	Fourth World Conference on Women – Beijing

1996 	Second United Nations Conference on Human Settlements – Istanbul

1996 	World Food Summit – Rome

1996  	Ninth Session of the United Nations Conference on Trade and Development –Medrand

1998	General Assembly Twentieth Special Session on the World Drug Problem – New York

Specific government targets and indicators can be found in Annex VI.2 The revised CCA Indicator Table contains details on the status of follow-up achievements attained and future challenges to be addressed.

# SECTION III: United Nations Co-ordinated Response and Co-operation Strategies

### III.1	Purpose of the UNDAF

The purpose of UNDAF in Lesotho is to orient, rationalise and encourage increased programmatic collaboration through a more systematic co-ordination the contributions of the various UN Agencies in order to strengthen national capacities and assist Lesotho to realise  its development goals. The UNDAF document seeks to summarise the United Nations System common response to Lesotho’s development challenges over the 2002-2007 co-operation period.  As a prerequisite to the implementation of the UNDAF, the UNCT in Lesotho has agreed to harmonise programme cycles beginning 2002.

UN Country Team has agreed on a six year UNDAF Cycle starting in 2002 to 2007.  The rationale for the selection stems from our different programme cycle durations ranging from two years for the specialised agencies such as WHO and FAO, five years for UNICEF, WFP and UNFPA, and three years rolling for UNDP.

The six-year UNDAF cycle will ensure that specialised agencies have three-year budget cycles within this period.  UNDP, UNICEF and UNFPA cycles will therefore commence from 2002-2007.

It should be noted that the first UNDAF for Lesotho is a forward looking UNDAF providing a basis for UN coordinated response to the development challenges of Lesotho from the period 2002-2007.  The strategic focus of the first UNDAF for Lesotho is to speed up the process towards halving poverty by 2015. The basis of the UNDAF is the Seventh National Development Plan priorities, national vision for Lesotho, development challenges emerging from the CCA analysis, Poverty Reduction Strategy Paper, LDC III, United Nations Poverty Strategy Action Plan.

The UNDAF will improve a co-ordinated follow-up to UN global conferences and support the implementation of international conventions and declarations.

### III.2	The Mission of the United Nations in Lesotho

The United Nations  in Lesotho is committed to support the Basotho nation, through the Government of Lesotho involving all stakeholders, to define and implement its strategic long-term development vision and  attain the global targets for sustainable human development it has committed to in the various UN global conferences and declarations.

Specifically, the UN Country Team will provide a co-ordinated response to Lesotho’s goal of halving extreme poverty by 2015 through:

- Reducing unemployment;

- Attaining sustainable livelihoods;

- Empowerment of women and achieving gender equity: through the elimination of discriminatory laws;

- Protect and regenerate the environment;

- Fight the HIV/AIDS pandemic: through support the National AIDS Policy and the implementation of the National AIDS Strategic Plan for 2000-2004;

- Improve the nutritional well-being of vulnerable groups;

- Improve the welfare of the Basotho children and other vulnerable groups;

- Foster respect for human rights, including children’s rights;

- Promote good governance, broad participation of citizen in decision-making and holding of free and fair elections whose results are generally accepted.

- Improve and ensure access to reproductive health facilities and services, and;

- Increase access to basic education for all: through supporting the Free Primary Education  policy approved by the Government of Lesotho in 2000

The UN Country Team will use the UNDAF as the main instrument to achieve its mission.

### III.3	Lessons learned from past United Nations Development Assistance

Although UN agency Country Programmes of assistance were developed  on an individual basis in the past, there has been extensive collaboration between and among UN agencies. Some of the key programmes of intensive collaboration involving no less than four agencies each include the Safe Motherhood Initiatives, HIV/AIDS Project, Preparation of Environmental Impact Assessment for the Lesotho Highlands Water Project, and Sectoral Round Table Consultative processes.

In the area of nutrition and health, the UN Agencies are working closely and numerous other donor organisations, such as European Union, World Bank, Ireland Aid, United States Peace Corps and DfID. For example, World Food Programme and UNDP have co-operated in providing food assistance to primary schools. In co-operation with the Africa 2000 project, WFP provided assistance with identification and distribution of Non-Food-Items as well as advice and extension work with teachers and pupils on developing self-reliance activities. In the area of food for capacity building and non-formal education, WFP was assisted by consultants from both UNESCO and ILO to conduct a feasibility study.

Addressing the needs of vulnerable groups, such as herdboys, has been an area of collaboration between UNFPA, WHO and UNICEF. However, progress has been hampered by lack of understanding the exact type of their needs, the magnitude of their problems, and poor co-ordination of efforts. The herd-boys study undertaken jointly by UNICEF and the National University of Lesotho has now provided answers to some of our questions.

Recognising that disaster preparedness and mitigation initiatives are vital in a country which frequently suffers from drought and severe snow falls, WFP has established a disaster management consultation group as a platform for policy dialogue. The Group includes the Disaster Management Authority, several government ministries, NGOs and UN Agencies, such as UNICEF.

Another area of common intervention is the public sector reform, which is supported by the UN System as well as DfID, SIDA, Ireland Aid, World Bank and the African Development Bank.

UN Agencies are increasingly mounting joint development and review of their country programmes.  UNICEF and UNDP are members of WFP's Country Programme Committee (CPC), a committee that has been set up together with the Government of Lesotho to ensure partners' input into the implementation and review of the WFP Country Programme.

From the few areas of collaboration and joint programming mentioned above, the UNCT has realised the benefits of working together. A key lesson learned is that the impact of programmes can be maximised through participatory programme planning, and  elimination of duplication.

### III.4	The Strategic Focus of the UNDAF

The UN Common Country Assessment analysis has identified the main challenges which have to be addressed in order to achieve the goal  of halving extreme poverty by 2015.  Since 1990, the proportion of population with monthly incomes of less than 80 Maloti has increased from 49 per cent in 1993 to 68 per cent by 1999.  In addition, income disparity has widened as indicated by the Gini coefficient which was 27 per cent in 1990 and now around 57 per cent.  Food security and nutrition indicators have also declined.  Overall provision and access to basic social services show a worrisome trend.   Although universal accessibility of primary health care facilities has improved in Lesotho, 20 per cent of the population still lack access to basic primary health care services.

HIV/AIDS is emerging as one of the major development concerns in Lesotho.  The UNAIDS estimated in 1999 that about 23.6 per cent of adults (15-49 years), that is an estimated 240,000 persons out of a population of about 2 million, are living with HIV (excluding those with AIDS) in Lesotho.  Overall enrolment rates have declined from 77.3 per cent in 1989 to 54.8 in 1998.  Persistently high drop out and repetition rates reflect on the decline in quality of primary education in Lesotho.  Adult literacy rates have remained stagnant at 38 per cent since 1985.  Provision of clean water supply and adequate sanitation facilities still remains a national challenge especially in rural areas.  Gender equality and women’s empowerment remain some of the most serious draw backs to overall national advancement, in particular, the legal status of women needs to be reviewed and equitable access by women to key decision making positions need urgent attention.  Environmental degradation continues to undermine sustainable food production, food security, employment and sustainable livelihoods.

Four key development challenges have emerged through the Common Country Assessment (CCA) consultative process, around which the UN agencies have developed four strategic objectives for intervention:

- Promoting Employment Creation and Income Generation;

- Enhancing good governance processes and institutional capacity building;

- Development of Basic Social Services to Vulnerable Groups (women, children and youth), and;

- Enhancing the sustainable management of natural resources.

These objectives form the basis of the UNDAF’s collaborative programming.  The UN Country Team in Lesotho is convinced that it is essential that the development challenges are dealt with as part of an integrated whole and that policy advice, funding, technical assistance, monitoring and direct programme interventions by the UN System are as co-ordinated and coherent as possible. It is also vital that these emerging development challenges are approached in the context of broader crosscutting issues, such as Gender Equality and Human Rights. Such issues are inseparable from these development challenges and must be mainstreamed into any future UN assistance at the country level within the UNDAF framework.

### III.5	UN System Strategic Objectives under the First UNDAF

Strategic Objective 1:  Promoting Employment Creation and Income Generation

A. Promoting Pro-poor and Pro-equity Macroeconomic and Social Policies

Despite the remarkable macro-economic growth experienced in Lesotho since the late 1980s, the analysis presented in the CCA suggests that income and human poverty suggest that overall levels have generally either stagnated or worsened over the past decade. As such, Lesotho shares the experience of many other Sub-Saharan African Least Developed Countries (LDCs), in that economic growth has proven not to be a sufficient condition for sustainable improvements in the livelihoods of the poorest groups. The UN System in Lesotho will advocate for engagement in public expenditure reviews that support increased budget allocations and expenditures for basic social services.  It will also ensure equity in access to basic social services by the most vulnerable groups among the poor, especially the children and the disabled.

- A national Vision for the year 2020 Charter is adopted.

- A comprehensive Poverty Reduction Strategy  is formulated in a nationally-owned and government-driven process.

- Viable mechanisms for poverty monitoring are developed.

- The impact of social and micro-economic policy reforms on reducing overall poverty levels are continuously assessed.

The main challenge for UN is to help the nation determine the identity of poverty and its underlying causes, and set forth policies, strategies and programmes for its eradication.

- Undertaking Poverty and Vulnerability Assessment

Poverty is wide spread, affecting both rural and urban communities.  In particular, Lesotho’s mountainous topography renders some communities inaccessible to normal development assistance.  These communities are also prone to persistent droughts, heavy snowfalls and floods.  In addition, pockets of widespread poverty exist in urban and peri-urban areas. There is generally lack of systematic and continuous monitoring of urban and peri-urban poverty.  Due to structural under-development, Lesotho’s ability to monitor poverty levels in these stricken communities remains relatively limited. Periodic poverty and vulnerability assessment are therefore necessary to identify poverty stricken communities, define targeting criteria and help suggest appropriate methods of intervention and monitoring. UN assistance will therefore:

- Advocate for a national debate on the principal dimensions of poverty in the country.

- Undertake the assessment and mapping of poverty, reflecting the national perspective and the multidimensionality of poverty, including the dimensions of gender and geographical differences, using qualitative and quantitative measures.

- Promote a wide and transparent dissemination of poverty data.

C. Employment Creation and Sustainable Livelihoods

One of the fundamental deficiencies in Lesotho's economic structure is the unequal way in which income is distributed. The situation is such that the more income distribution is skewed at the expense of the poorest, economic growth alone cannot alleviate poverty. Therefore, efforts to deliberately bias the benefits of economic expansion towards the poorest groups become crucial. Generating reliable sources of income for these groups by creating employment is, therefore, a vital part of the UN System assistance to Lesotho, which will focus on :

- Re-integration of retrenched mineworkers.

- Establishment of small and medium enterprises (SMEs).

- Expansion and improvement of the informal sector.

- Supporting the establishment of a micro-credit facilities to vulnerable groups.

- Supporting and promoting labour intensive development projects.

Strategic Objective 2:  Enhancing Good Governance Processes and Institutional Capacity Building

A. Good Governance

Closely linked with the reduction of poverty is the strengthening of governance institutions.   The critical players in country’s politics since independence have been the political parties, armed forces, the chieftainship and the monarchy.  It is mainly the interplay of relationships among these institutions that has shaped the nature of governance in Lesotho and seems likely to continue to play a central role.   Granted, these problems are not unique only to Lesotho but, the key single factor which exacerbates the country’s problems is the apparent lack of institutional capacity to resolve conflicts peacefully which seems to be at the core of the country’s continuing governance crisis.  The UN’s interventions in the area of governance would be in the following:

- Consolidation of democratic processes and strengthening of governance institutions.

- Enhancing national capacity for conflict resolution and management.

- Depolitisation of public sector institutions, armed forces and civil service.

- Development of strong civil society.

- Decentralisation and devolution of power to local authorities.

- Assistance with the electoral process and voter education.

- Support to national institutions in the fight against corruption and economic offences.

B. Strengthen National Capacity for Development Management and Policy Implementation

Lesotho has a number of political, economic, administrative and sectoral reform processes such as Public Sector reform, agriculture sector reform and health reform aimed at improving the delivery and quality of services. 	Lesotho is also implementing a decentralisation programme, to ensure greater local level participation, involvement and ownership, which is essential for economic, social and political progress. However lack of capacity has constrained the effective implementation of these programmes, hence delaying the achievement of the aspirations of the people. The Government of Lesotho therefore needs UN assistance to:

- Support and strengthen Government capacity to formulate, develop, analyse and monitor development plans and co-ordinate public sector reforms.

- Promote transparent, accountable and participatory governance processes.

- Increase community ownership of development processes, especially through stronger community –based organisations.

C. Promote Fundamental Human Rights and Peoples Empowerment

The promotion of human rights and peoples empowerment is both a moral imperative and a necessary approach to the eradication of poverty. Basically, the constitution of Lesotho guarantees fundamental human rights and freedoms to all persons regardless of race, colour, sex, language, religion and political or other opinion.  The rights and freedoms prescribed within it fall into the domain of civil and political rights, such as the right to life, personal liberty, freedom of movement, freedom from inhumane treatment, and right to a fair trial.  In contrast, those that fall into the category of social, economic and cultural rights are set up in the Constitution only as Principle of State Policy, not enforceable by any court.  These Principles of State Policy are subject to the limits of the economic capacity and development of Lesotho, and are to guide the authorities in the performance of their functions.  The serious problem that arise is that these policies are not translated into law, and so do not offer the same level of protection to those whose economic, social or cultural rights are not legalised. Such strategies will include:

- Support for the development of new legislation, which seeks to protect fundamental human rights and ensures national follow-ups to the UN conventions, treaties and declarations.

- Promoting the adoption of rights based approaches to the eradication of poverty.

- Monitoring  follow-ups to UN Human Rights Conventions and Declarations; especially with regards to Rights of the Child and advancement of women.

- Development of Human Rights Culture and the need for a permanent National Human Rights Commission.

- Strengthening and monitoring of the Administration of Justice and Legal Systems.

D. Gender Equality and Women’s Empowerment

Despite the fact that women bear most of the responsibility for managing the household and constitute the majority of the labour force in the country at senior technical and professional levels, their social and legal status remains low.  Therefore, although gender equality espouses the development of both women and men, any analysis of gender issues in Lesotho will necessarily have to focus on women’s socio-economic role.  One of the most central concerns regarding the position of women in Lesotho is the existence of gender-biased laws. UN System will provide support for:

- Implementation of CEDAW, ECOSOC and Beijing +5 recommendations for improving gender equality and empowerment.

- Finalisation and implementation of National Gender Policy.

- Formal and informal education for herdboys.

- Gender sensitisation and the development of a culture of gender equality and equity in women’s access to decision-making positions in society.

E. Child Rights

Child abuse and neglect, both domestic and institutional, is a serious problem in Lesotho.  Family violence, sexual abuse of children and other forms of abuse are not always reported, so it is difficult to refer to any reliable statistical data.  Recently, there have been cases of child abuse and neglect reported in some centres that provide residential care for children.  The fact that this problem is getting more public attention in Lesotho indicates that it exists and that it has to be addressed seriously and systematically. The UN System will provide  support for:

- Monitoring the implementation of UN Convention on the Rights of the Child.

- Strengthen of protection mechanisms and building of institutional capacity to deal with street children.

- Protection of AIDS orphans.

- Increased monitoring of child abuse and neglect.

- Co-ordinated approach to addressing the issue of herdboys.

Strategic Objective 3: Development of Basic Social Services to Vulnerable Groups (Women, Children and Youth)

A. Primary Health Care and Reproductive Health

The country’s mountainous terrain makes access to health facilities in many rural areas very difficult.  In March 1979, the Government of Lesotho endorsed the concept of Primary Health Care (PHC) and thus embarked on a long road towards universal health coverage.  In the 20 years since the adoption of PHC, Lesotho has made major achievements in terms of assuring and increasing access to health services.  However, the major problems encountered with the implementation of PHC has been on how to assure its sustainability.  The persistent problems of severe shortages of staff, poor remuneration packages, equipment have all combined to adversely affect the assurance of continued and sustainable implementation of PHC. UN assistance will:

- Strengthen the co-ordination and implementation of the health sector investment programme in the Ministry of Health.

- To improve delivery of basic health services, especially to disadvantaged groups.

- The quality and reliability of data for monitoring geographic inequalities in selected health indicators.

B. Basic Education

Following independence in 1966, Lesotho made remarkable strides in raising the country’s educational and literacy standards.  However, in the past decade there has been a gradual decline in both the qualitative and quantitative levels of education.  Despite official aims of increasing access to education, overall enrolment in primary schools has displayed a worrisome trend during the 1990s.  The latest available data suggest that around 60 per cent of children 6-12 years of age – the official primary school age – attended primary school in 1997, compared to 76 per cent in 1990.  Especially the enrolment rates for girls have declined. There are several factors driving these disturbing developments including: weak school management, inadequate school facilities and teaching materials, overcrowded and understaffed classrooms. The UN assistance will be in the following areas:

- Support the programme of Free Primary Education.

- Promote gender equality in education.

- Increase literacy rates, with special emphasis on male literacy.

- Support vocational skills training particularly for vulnerable groups.

C. Drinking Water and Sanitation Facilities

In Lesotho, half a million people have no access to safe drinking water and adequate sanitation facilities.  These impact most heavily on women and children in rural and peri-urban areas.  In addition, there is a disturbing increase in inadequately designed or operated waterborne sewerage where the impact on the health of the community and the pollution of the environment is extremely serious.  Inadequate lower levels of services may well pose less of a threat than failed high level services.  These inadequate facilities combined with unhygienic practices and a general lack of formal water supplies, as well as safe disposal of other domestic wastewater, represents Lesotho’s sanitation problem.  Therefore, in order to improve the health and quality of life for the whole population, the UN’s focus will be in the following areas:

- Improve access to safe drinking water.

- Improve access to safe sanitation.

D. Food Security

Food insecurity in Lesotho is caused by wide inter-annual fluctuations in production as a consequences of the weather, exacerbated by landlessness, unemployment and lack of a stable income with which to buy food.  The most food insecure groups of the population are geographically concentrated in the mountains and drought-prone areas such as Mafeteng and Senqu river valley.  The categories most vulnerable to food insecurity are female-headed households, landless households without livestock or  casual labourers, unemployed youths and old people with land, but insufficient labour and capital to use it productively.

- Strengthen the Disaster Management Authority (DMA).

- Promote access to basic foodstuffs at free market prices.

- Promote equitable distribution of foodstuff.

E. HIV/AIDS

Considering the  speed with which the HIV/AIDS pandemic has spread through Southern Africa and the potentially devastating effects it has on human capabilities, the combat against HIV/AIDS is of highest priority in Lesotho.  The remarkable progress that Lesotho has made in many health and social indicators over the past decade are under severe pressure if the disease and its destructive consequences go unchecked.  The UN’s interventions will be in the following areas:

- Implementation of National Strategic Plan on HIV/AIDS.

- Strengthening of National AIDS Prevention and Control Programme.

- Intensifying HIV/AIDS awareness campaigns.

- Collection of reliable data and implementation of consistent surveillance systems.

- Strengthening of coordination and information sharing to minimise reversals in development gains.

- Facilitating a Round Table Conference to mobilise financial assistance in the fight against HIV/AIDS.

Strategic Objective 4: Enhancing the sustainable management of natural resources

A. Natural Resource Management

Lesotho is an agrarian economy with the agricultural sector employing more than 80 per cent of the population.  However, the percentage of total arable land presently makes up less then 10 percent of total land area. Reasons for this include overgrazing of rangelands, urban sprawl, erosion and poor environmental management. Protecting Lesotho's natural resources for future generations is one of the most urgent tasks at hand.  Fundamental problems of Lesotho land tenure, that is lack of land security prevents land and agricultural development conducive to attract investment at the same time being pro-poor – allowing rural household access and long term security.  UN assistance, therefore, will:

- Promote secure land tenure for the rural and urban poor which guarantees legal protection against forced eviction, harassment and other threats.

- Support policies that increase access to land, particularly to the rural households.

- Support land use planing, soil conservation, and the coordination of natural resource management initiatives.

B. Promoting increased Food Production

The environment has long been a focus of the UN System's assistance to Lesotho, both with regards to environmental protection as mentioned above, and with regards to attaining sustainable food security. Even at present, despite the high concentration of the population in rural areas, the poorest sectors of Basotho society are highly dependent on purchased food to meet their daily nutritional requirements.  The UN system will:

- Support crop diversification strategies.

- Support value adding land husbandry practices.

- Improve input and extension service delivery to farmers.

- Support micro-credit/grant schemes to rural farmers.

STRATEGIC OBJECTIVES, PRIORITIES FROM CCA AND THE UN RESPONSE

STRATEGIC OBJECTIVE 1:  Promoting Employment Creation and Income Generation

1.1	Promoting Pro-Poor and Pro-Equity Macro-Economic and Social Policies

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To promote sustainable economic growth and minimise the high inequity in income distribution. To create a conducive environment for investment. | Definition of a clear long term vision 2020 Formation of a comprehensive poverty reduction strategy Development of a poverty monitoring framework and setting poverty lines for Lesotho Assessment of the impact of social and micro-economic policy reforms on reducing overall poverty levels. | World Bank UNDP UNICEF FAO UNFPA IFAD |

1.2	Undertaking Poverty and Vulnerability Assessment

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To hasten the pace of human development programme especially in geographically disadvantaged mountain areas. | Advocate for a national debate on the principal dimensions of poverty in the country. Undertake the assessment and mapping of poverty reflecting the national perspective and the multi dimensionality of poverty including the dimensions of gender, and geographic differences, using qualitative and quantitative measures. Promote a wide and transparent dissemination of poverty data | UNDP UNICEF WHO WB FAO WFP |

1.3 	Employment Creation and Sustainable Livelihoods

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| Promoting lateral and vertical expansion of the formal sector. Increasing productivity and income in the informal sector Transforming the agriculture sector from subsistence production to market oriented production. Universal access to paid employment | Reintegration of retrenched mine workers into the economy Establishment of small and medium enterprises Expansion and improvement of the informal sector Establishment of a micro-credit centre Supporting and promoting labour intensive community development projects Trade strategy formulation Introduce concept of Export Production Villages (EPVs) | UNDP UNIDO ILO FAO WB WFP ITC |

STRATEGIC OBJECTIVE 2:  Enhancing Good Governance Processes and Build Institutional Capacity

2.1	Good Governance

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| Democratic consolidation, to engender respect for the constitution and protect and develop democratic institutions. Public sector reform, to restructure and right-size the civil service and to introduce mechanisms to improve effectiveness and efficiency in service delivery and productivity in the civil service. Decentralisation of power and resources to local communities. | Consolidation of democratic processes and strengthening of institutions Enhancing national capacity for conflict resolution and management Depoliticisation of public sector institutions, armed forces and civil service Development of a strong civil society Decentralisation and devolution of power to local authorities Assistance with the electoral process and voter education | UNIFEM UNDP UNFPA WB |

2.2	Strengthen National Capacity for Development Management and Policy Implementation

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To re-engineer the planning system to improve the coordination monitoring and evaluation and policy management. To promote partnerships with all stakeholders in all planning and implementation processes. | Support and strengthen government capacity to formulate, develop, analyse and monitor development plans and programmes Promote transparent accountable and participatory governance processes Promote increased community ownership of development processes, especially through stronger community-based organisations Provide assistance for coordination of external donor support. | World Bank UNFPA UNICEF UNDP |

2.3	Promote Fundamental Human Rights and People Empowerment

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| Approve the establishment of a National Human Rights Commission Disseminate information on human rights Ensure compatibility of domestic legislation with international human rights instruments | Support the development of new legislation, which seeks to protect fundamental human rights and ensures national follow-ups to the UN conventions, treaties and declarations Promote the adoption of rights based approaches to the eradication of poverty Support the development of human rights culture and the establishment of a permanent human right commission. Strengthen and monitor the administration of justice and legal systems. | UNICEF UNDP UNIFEM UNFPA UNHCR UNESCO |

2.4	Gender Equality and Women’s Empowerment

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To finalise a national gender policy To review and revise all laws which discriminate against women To put measures in place against discrimination, exclusion or restriction on the basis of sex To enforce equal opportunity in education by law Equal participation in decision making. | Support the implementation of CEDAW, ECOSOC and Beijing + 5 recommendations for improving gender equality and empowerment in the country Support finalisation and implementation of a national gender policy Support formal and informal herdboys education Advocate gender sensitisation and development of a culture of gender equality Monitor and evaluate the level of gender sensitivity in all proposed development projects and plans Introduction of gender studies in all institutions of higher learning, including NUL, NHTC, LEC, LAC, etc. Introduce legal literacy campaigns and programmes to make public sensitive to gender issues Attainment of SADC 30% quota by 2005. | UNCT Government Ministries and other Bilaterals, UNICEF UNFPA UNIC UNDP FAO WFP WHO |

2.4	Child’s Rights

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To eliminate child labour To develop programmes focusing on herdboys in the 7th National Development Plan To introduce the Targeted Equity Based Programme (TEBP) to cover children from poor households not in FPE Scheme To put the rights and needs of children at the very centre of development strategy To improve the protection of children in especially difficult circumstances | Monitoring and implementation of UN convention on the Rights of the Child Strengthening protection mechanisms and building institutional capacity to deal with street children Protection of AIDS orphans Increased monitoring of child abuse and neglect Address the issue of herdboys in a coordinated manner. |  |

STRATEGIC OBJECTIVE 3:  Development of Basic Social Services and Increasing their Accessibility to Vulnerable Groups (Women, Children and Youth)

3.1	Primary Health Care and Reproductive Health

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To improve delivery of basic health services, especially to disadvantaged groups To reduce infant mortality rate To reduce child mortality rate To improve maternal health and reduce maternal mortality rate To increase access to family planning To maintain and increase high levels of immunisation coverage To develop policies, procedures and guidelines for all priority health services To increase equitable access to quality reproductive health care for women, men, youth and children | Strengthen the coordination and implementation of the health sector investment programme in the MOH Improve delivery of basic health services especially to disadvantaged groups Improve the quality and reliability of health data for monitoring geographic inequalities in selection health indicators Strengthening family planning services Contraceptive distribution Promotion of child-spacing Promotion of safe motherhood Advocacy for the reduction of harmful traditional practises Create awareness on sexual related violence | WHO UNICEF UNFPA |

3.2	Basic Education

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To increase primary school enrolment rate To embark on a programme of Free Primary Education To reduce adult illiteracy | Support the programme of Free Primary Education Promote gender equality in education Increase literacy rate with special emphasis on male literacy Support vocational skills training, particularly for vulnerable groups | UNICEF WFP UNDP |

3.3	Drinking Water and Sanitation Facilities

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To increase access to safe drinking water To increase access to latrines | Improve access to safe drinking water Improve access to safe sanitation Encourage the use of sustainable technologies in the provision of water and sanitation especially in the rural areas Assist development of Waste Management Action Plan | UNICEF ILO WHO |

3.4	Food Security and Nutrition

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To ensure household food security. To reduce malnutrition amongst under fives Disaster management preparedness Impact assessment of policy reforms to date and to determine additional constraints | Strengthen the Disaster Management Authority (DMA) Promote access to basic food stuff at free market prices Promote equitable distribution of food stuff Programme for use of traditional food Promote combination of employment and food production in agriculture to ensure dual income and access to food. Assistance to implementation of National Disaster Management Preparedness Plan | UNDP UNICEF WFP IFAD FAO |

3.5	HIV/AIDS

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To reduce HIV/AIDS sero prevalence 100% coverage of PLWHAS through support and care 100% of AIDS orphans cared for Spread of HIV/AIDS among 15-49 years olds reduced Behavioural change regarding HIV/AIDS among the general public increased | Support implementation of National HIV/AIDS Policy and National Strategic Plan Strengthen National AIDS Prevention and Control Programme Intensification of AIDS awareness campaigns Collection and collation of reliable data and implementation of consistent surveillance systems Strengthening of coordination and information sharing to minimise reversal development gains Promote use of condoms Protection of AIDS orphans Ensure quality of blood transfusion services Promotion of the rights of PLWHA | UNDP UNAIDS WHO UNICEF WFP FAO WB UNFPA |

STRATEGIC OBJECTIVE 4:  Enhancing the Sustainable Management of Natural Resources

4.1	Natural Resource Management

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To reverse current trends in environmental degradation Make land tenure especially women’s right to land more secure To improve rangeland capacity to sustain better quality livestock To refocus the LHRF on poverty alleviation projects including public works in rural areas to arrest soil erosion and environmental degradation | Promotion of secure land tenure for the rural and urban poor which guarantees legal protection against forced eviction, harassment and other threats Support policies that ensure increased access to land, particularly for rural households Support land use planning, soil conservation and the coordination of natural resource management initiatives Promote environmental protection Strengthening of NEAP and implementation Enforce EIA Combat soil erosion and further loss of arable land Promote land reclamation Promote coordination of Natural Resource Management Protect the fragile mountain ecosystem and biodiversity | UNDP FAO WFP UNIDO WHO World Bank IFAD |

4.2	Promoting increased Food Production

| National Priorities | Areas of UN Assistance and Proposed Strategies | Collaborating Agencies |
| --- | --- | --- |
| To remove price and market distortions for maize and sorghum Invest in rural infrastructure that supports intensified agriculture and the production of export crops To emphasise agricultural diversification To re-orient agricultural support services and capacity building to be more user-driven rather than supply-driven. To fine-tune agricultural policy to support the development of the sector | Support livestock and crop diversification strategies Support value adding and husbandry practises Improve input and extension service delivery to farmers Support micro-credit/grant schemes to rural farmers Focus on improving female farmer’s access to land and services Technological improvements and development | FAO WFP IFAD |

# SECTION IV: FOLLOW Up and REVIEW

### IV.1	Implementation Arrangements

In order to ensure the greatest possible impact of UN activities, the implementation arrangements of the UNDAF in Lesotho comprise a variety of interrelated levels; starting with the Office of the Resident Coordinator and the UNCT, the UN Inter-Agency CCA/UNDAF Task Force and reaching out to the Government, bilateral donors, NGOs through the extensive network of the UN Thematic Groups and Technical Working Groups.

### IV.2	The Resident Co-ordinator System in Lesotho

The Office of the Resident Co-ordinator of the UN System’s operational activities for development ensures  effective complementary and synergistic contributions of the UN System, and fosters a collegial team approach to leadership. The Resident Co-ordinator assumes, on behalf of the UN System, and in consultation with the other representatives, overall responsibility for, and co-ordination of, the system’s operational activities carried out at the country level.  The UN Resident Co-ordinator in Lesotho is also helping to orchestrate the full intellectual and technical resources of the UN System in support of national development.

The UNCT in Lesotho includes the United Nations Development Programme, United Nations Children’s Fund, World Health Organisation, World Bank, World Food Programme, United Nations Population Fund, Food and Agriculture Organisation of the United Nations and United Nations Information Centre. Other agencies cover Lesotho but are based in the neighbouring countries, especially in the Republic of South Africa. These include the Office of the UN High Commissioner for Refugees (UNHCR), the UN High Commissioner for Human Rights (UNHCHR), the United Nations Industrial Development Organisation (UNIDO) and United Nations Office for Drug Control and Crime Prevention (UNODCCP). These agencies collaborate under the UN Resident Co-ordinator.  All agencies resident in Lesotho are housed under one roof at The UN House in Maseru, with the exception of WFP, which occupies an adjoining complex close to the UN House

Several Common Services initiatives have also become operational since moving into the UN House. A Memorandum of Understanding on the occupancy and the use of the Common Premises was signed by all Agencies, with the exception of UNICEF. The Common Services Account became effective in 1997 with the participation of those agencies that share the UN House premises, i.e. UNDP, UNICEF, FAO, WHO, UNFPA and World Bank. The common services include security, cleaning, maintenance and repairs of facilities, waste removal, garden maintenance, water and electricity supply, telephone services, receptionist and general services such as satellite connectivity connecting all agencies, web page, UN Newsletter. In addition, the cafeteria, banking facilities and travel agent have been secured for UN house for the benefit of all UN staff and facilitation of their work. The Common Services Account has proved to be more effective and provides better quality services and has improved cooperation among the UN Agencies.

The production of the UN in Lesotho newsletter and web page, joint press conferences, celebration of UN International Days and other events, spearheaded by the theme groups, have created much greater visibility for the UN System, and awareness of UN programmes, projects and activities in general. There is demonstrably greater understanding of the activities of the UN System, and enhanced appreciation for its presence in Lesotho. All these collaborative efforts constitute positive indicators for strengthened partnership and teamwork by the UN Country Team in Lesotho.

### IV.3	UN Inter-Agency Theme Groups

In order to enhance UN collaboration and cooperation, UN Theme Groups and Technical Working Groups were established as essential instruments for improving information sharing and co-ordination efforts of the UN System. These Theme Groups cover the areas of:

- HIV/AIDS

- Poverty, Food and Nutrition

- Good Governance and Human Rights

- Environment, Sanitation and Water

- Gender and Reproductive Health

Main accomplishment after their formation in 1999 was their contribution to the production of  CCA. Although most were involved in preparing for the celebration of UN days relating to their thematic area, only HIV/AIDS and Reproductive Health carried out any substantial operational activities.

The UN Theme Group on HIV/AIDS comprises representatives from all UN Agencies resident in Lesotho.  The United States Ambassador is a member and is also Co-chairing  the Theme Group with UNICEF. The Chairmanship of the Theme Group is on rotational basis and presently, UNICEF is the Chair.  The Theme Group is supported by a Technical Working Group composed of selected professional staff from all agencies.

The prevalence of HIV/AIDS and related diseases in Lesotho has ensured that the Technical Working Group (TWG) on HIV/AIDS remains extremely active. This is the working group that reports to the Theme Group. The TWG was established to meet frequently to deal with the technical issues. This TWG comprises focal points from all the UN Agencies resident in Lesotho and the Manager  of the Lesotho AIDS Programme Coordinating Authority (LAPCA).  Co-opting the LAPCA Manager into the TWG has harmonised the process of identification of priority areas and the subsequent writing of proposals submitted to UNAIDS for funding.

Both the Theme Group and the Technical Working Groups meet once every month.  The scope of the groups' activities and discussions spans across a variety of issues pertaining to HIV/AIDS in Lesotho. These include such activities as support for the completion and implementation of the HIV/AIDS policy and the implementation of the National AIDS Strategic Plan. It was agreed that there was need to increase the number of bilateral and multilateral donors, Government, NGOs  in the Theme Group activities.  The HIV/IADS Theme Group has been expanded accordingly.

The Theme Group on Poverty, Food and Nutrition comprises the heads of all UN Agencies in Lesotho and is -co-chaired by FAO and UNDP. The Theme Group brings together the UN System, acknowledging that in spite of the distinct backgrounds and specialised focuses of each of the agencies all adhere to an overarching goal of alleviating poverty in Lesotho. As such the Theme Group on Poverty Reduction reaches across the thematic areas of all the other Theme Groups and is supported by the strong inter-agency collaboration that already exist.

Currently, the Theme Group is engaged in two activities. The first includes the elaboration of a UN System approach to the Government-driven process of designing a Poverty Reduction Strategy  for Lesotho. This work is closely related to the UNDAF context and is set to operationalise the UN's poverty interventions in the usual close cooperation with the Government of Lesotho .

The second activity of the Theme Group concerns the preparation of the second National Human Development Report (NHDR) for Lesotho. It has been decided that the NHDR will carry the overarching theme of Poverty Reduction and the Poverty Reduction Team of UNDP is co-ordinating this activity through the Government's Technical Working Group to formulate a Poverty Strategy Reduction Paper (PRSP). The NHDR is set to focus on synthesising the various surveys and studies on the poverty situation, stimulate debate and strengthen capacities for analysing and monitoring poverty in Lesotho.  The focus of the Theme Group will be broadened to include: nutrition, food security and disaster management.

After its foundation in March 1999, the Theme Group on Good Governance and Human Rights consisting of UNDP and UNICEF (Co-Chairs), as well as WHO and UNIC proceeded by preparing its Terms of Reference. In order to establish a comprehensive overview over Good Governance and Human Rights activities in Lesotho, the Theme Group compiled an inventory of organisations working in these areas. Liasing with the Government of Lesotho, the Theme Group distributed the Constitution of Lesotho widely to stakeholders. In addition, the Theme Group participated in the preparation of the CCA, in particular in the development of indicators.

The Theme Group on Environment, Sanitation and Water was established in May 1999 and currently comprises four agencies, namely UNDP and WHO (Co-Chairs), as well as UNICEF and the Africa 2000 Network. While the Theme Group originally met on an ad hoc basis, it has been agreed that future meetings will be scheduled regularly.

Since its inception and drafting of the Terms of Reference, the Theme Group has been active in a variety of areas. In its function as a focal point for all activities centring on environment, water and sanitation, it has corresponded with the Ministry of Development Planning in order to bring the Government of Lesotho as well as other stakeholders on board. The Theme Group is seen as catalysing a broader, but closely linked National Consultative Forum on Environment.

The Theme Group has contributed to the "Environment, water and sanitation" chapter of the CCA and has participated in the World Environment and World Desertification Days celebrations, in Berea and Mafeteng districts.

The Theme Group on Gender and Reproductive Health presently consists of WHO (Chair), UNFPA, UNICEF, UNIC, UNDP, FAO and WFP.  As the Theme Group is relatively small, it also acts as Technical Working Group. The Theme Group has developed its Terms of Reference. The major activity undertaken was  to provide guidance to the Ministry of Environment, Gender and Youth Affairs to develop the national Gender Policy.

The Theme Groups is very actively playing an advocacy role in various gender issues in Lesotho.   In particular, the Theme Group is engaging the Government of Lesotho, NGOs and other civic organisation to promote awareness for eliminating violence against women, child abuse, rape and all discriminatory laws against women.

### IV.4	Expected Use of UNDAF for Advocacy, Policy Dialogue and Aid Coordination

External assistance in Lesotho plays a major role in financing development programmes and projects for overall socio-economic development of the country and particularly in the implementation of poverty alleviation strategies.

In recent years, however, external aid has declined globally and this trend has affected Lesotho greatly. According to figures from the OECD Development Assistance Committee, Lesotho received a total of USD 66 million in ODA in 1998: the lowest level since the late 1970’s, and in real terms less than one third compared to the peak of the early 1980’s. In per capita terms, aid has dropped from USD 73 a head in 1983 to USD 32 in 1998. Given this trend and the importance of the external aid to the Government of Lesotho, the UNDAF will be used as a tool to mobilise resources and improve the effectiveness of available resources.

### IV.5	Institutional Arrangements and Commitments

The Ministry of Development Planning, through the Department of Economic Cooperation has the mandate and the responsibility of co-ordinating and managing the external assistance. UNDP has been supporting the Government of Lesotho with the main aim of poverty alleviation programmes through key areas of technical assistance focusing on:

- Capacity Building

- Resource Mobilisation

- Policy development

- Facilitating Technical Cooperation among Developing Countries

- Co-ordination of United Nations Operational Activities for Development

- Infrastructure Development

- Advocacy and Advisory Services

Currently, the Department of Economic Cooperation is embarking upon the formulation and development of a National Aid Policy and setting up appropriate computerised Aid Management Information System to capture and monitor external aid flows.  This will ultimately allow the Ministry of Development Planning the capacity for better managing, co-ordinate more effectively the utilisation of external assistance.

### IV.6	Strengthening Development Partnerships

A critical element in the UN System’s organisations and the Government’s relations with its partners, and government access to aid resources is the development and adoption of the poverty reduction strategy. The Poverty Reduction Strategy Paper (PRSP), which is currently being prepared is expected to improve the effectiveness of the financial resources management and targeting of poverty reduction programmes to the most vulnerable segments of the population through the design, implementation and monitoring of pro-poor policies.

The UN System intends to boost external partners to help strengthen aid co-ordination and management through a stronger emphasis on comprehensive and nationally-owned programmes as an alternative to the traditional project approach.

The programme approach could act as a catalyst for major institutional development focusing on impact rather than the management of inputs. It systematises efforts in inter-sectoral and multi-institutional sectors, avoids duplication of effort. Above all, the programme approach will support the UNDAF programming framework and facilitate the Government’s co-ordination among different donor agencies.

UN agencies in partnership with the Government of Lesotho should focus and share with other donors the advantages of a coordinated response framework offered by UNDAF first, as a value adding approach to increasing the impact development assistance.  Secondly, as a more deliberate attempt to focus development assistance to country’s strategic priorities for development.  The UNDAF will help strengthen Lesotho’s capacity to better manage UN System Aid flows.

To maximise the UNDAF as a tool for Aid Co-ordination, it is recommended to periodically undertake joint monitoring and evaluation of development programmes.  This mechanism could be further developed and widely applied, with a view to learn together, and progressively maximise the strength of the approach, the lessons of achievements and failures.

On the side of the Government of Lesotho, with assistance and networking of UN System could improve the coherence between external partners’ development cooperation policies including disbursement formalities and procurement procedures affecting the Government. This initiative has already started with the World Bank under the auspices of UNDP initiative for Government of Lesotho/International Organisations/Donors Co-ordination meeting on Procurement Reform Initiative. Through such initiatives, transparency of donor and government interest and mutual trust could be enhanced through continuous dialogue.

UNDP has facilitated no less than eight Round table Conferences: The Round Table mechanism has been the main modality for resource mobilisation.

Whilst the Round Table Conferences have attracted million of dollars in pledges, follow-up of these pledges have been unsatisfactory.  The UNDAF will be used as the main instrument to follow-up on Round Table pledges as a means to adding value to the development financing for Lesotho.

### IV.7	Monitoring and Evaluation Plan

In order to ensure that activities under the UNDAF continue to be of relevance to the development situation in Lesotho and that timely corrective action is fostered, the UN Country Team has agreed on a number of follow-up mechanisms. These are:

- Identification of specific and quantifiable targets in each area of assistance, based on the CCA database which is to be continuously developed in close collaboration with Government agencies.

- In-depth involvement of the inter-agency Theme Groups in assessing progress in their areas of expertise.

- Tripartite reviews and an in-depth evaluation of activities in each focus area

- An annual UNCT Review.

- Joint UNCT regular meetings (at least quarterly) with relevant ministries to be able to better meet the needs of Lesotho and to be responsive to current changes.

- UN/Government of Lesotho midterm review of UNDAF to assess continuing relevance and any remedial action.

- External and independent review at end of UNDAF cycle to plan for next cycle.

Furthermore, the annual Report of the Resident Co-ordinator will continue to serve as a tool for comprehensively analysing the previous year's achievements and challenges, and serves to assess the development situation of the country on a regular basis. The Report also articulates the subsequent year's work plan, including desired key results of the Resident Co-ordinator System.

# SECTION V: RESOURCE USE

### V.1	The Common Resources Framework

Over the 2002-2007 period covered by this UNDAF, the total anticipated resources to be mobilised through the UN System in support of UNDAF strategies will be finalised and inserted following approval of individual agencies’ cooperation programmes and frameworks. The tables below summarise the level of funding by major UN strategic objectives and by Agency.  It is expected that harmonisation of programmes cycles will greatly enhance the Country Team's ability to make efficient use of the declining resources. (The table will be updated as the country programme formulation process develops during 2001).

United Nations Planned or Estimated Resource Allocations by Agencies

(2001 - 2004)

| Agency | Strategic Objective 1 | Strategic Objective 2 | Strategic Objective 3 | Strategic Objective 4 | Projected Totals |
| --- | --- | --- | --- | --- | --- |
| FAO |  | Analysis of agricultural Census Data: $ 187 000 |  | Food Security through Water Control: $ 294 000 |  |
| UNDP | Poverty Reduction Development of Poverty Reduction Programme to support the implementation of PRSP: $ 3 000 000 | Governance: $ 2 891 200 Support to Conflict Resolution and Conflict Management. Support political and electoral reform including holding of next general elections. $ 500 000 | UNDP accelerated Response to HIV / AIDS: $ Human Capacity Building: $ 1 326 913 | Environment: $ 3 471 575 Conserving Biodiversity and enhancing environmental rehabilitation. Urban solid waste management $ 500 000 Promoting new and renewable resources of energy. |  |
| UNFPA |  | Population and Development Strategies: $ 500 000 Advocacy for Gender Equality: $ 300 000 | Reproductive Health: $ 1 500 000 |  |  |
| UNICEF |  | Promotion of Community needs assessment and participation: $ 2 279 300 Advocacy for Children and Gender Equality: $ 858 700 | Primary Education, NFE $ 4 174 600 Reproductive Health, Community-based Health Service: $ 1 385 200 ECDCs, immunisation: $ 3 301 800 | Food Security, water supply: $ 1 903 400 |  |
| WFP | Food for work: $ 224 482 |  | Food for capacity building in vocational training: $ 150 107 Food assistance to Primary Schools: $ 4 987 006 ECDCs: $ 457 840 | Disaster Preparedness: $ 278 360 |  |
| WHO |  | Assistance to Health System: $ 292 000 Immunisation campaigns and strengthening of government capacity: $ 969 440 | Mother and Child Health Care and Nutrition: $ 317 000 Hygiene Education and Emergency Response: $ 140 000 Health Promotion Activities and Social Welfare: $ 247 585 |  |  |
| TOTAL |  |  |  |  |  |

Source: UN Agency Country Programmes of FAO, UNDP, UNFPA, UNICEF, WFP, WHO

# SECTION VI: ANNEXES

### VI.1 	Lesotho’s UNDAF Work Plan

| Key Task | Responsible Person | Time Frame |
| --- | --- | --- |
| 1. Overall co-ordination, liaison with Resident Coordinator & UN Country Team and convenor of meetings | Ms. Chandiwana (assisted by Ms. Addis) | July – October 2000 |
| 2. Taking of minutes & meeting administrative requirements of Task Force | Ms. Addis | July – August 2000 |
| 3. Drawing up of TORs for Task Force | UNDAF Task Force | 10 July 2000 |
| 4. Drawing up of Work Plan | UNDAF Task Force | 10 July 2000 |
| 5. Collection of Agency country programmes | Ms. Addis | July 2000 |
| 6. Review of current Agency country programmes | UNDAF Task Force | July 2000 |
| 7. Review of final chapter of Lesotho’s CCA, and defining of opportunities for UN System support emerging from CCA | UNDAF Task Force | July 2000 |
| 8. Data collection from Agencies & stakeholders and liaison with Theme Groups: | UNDAF Task Force | July – September 2000 |
| a. Environment, Sanitation & Water | Ms. Mdee | July, August, September 2000 |
| b. Poverty Reduction, Food & Nutrition | Ms. Letete | July, August, September 2000 |
| c. Gender |  | July, August, September 2000 |
| d. HIV/AIDS & Reproductive Health | Ms. Mokose | July, August, September 2000 |
| e. Governance & Human Rights | Dr. Haile-Selassie | July, August, September 2000 |
| 9. Collation of information that is submitted | UNDAF Task Force | August - September 2000 |
| 10. Developing a working outline of the UNDAF document | UNDAF Task Force | July / August 2000 |
| 11. Consultation with development partners on emerging contents of UNDAF | UNDAF Task Force / UNCT | August / September 2000 |
| 12. Review & updating of CCA Indicators | UNDAF Task Force | August / September 2000 |
| 13. Zero Draft of UNDAF document | UNDAF Task Force | Early October 2000 |
| 14. Presentation of draft UNDAF to UNCT | UNDAF Task Force | October 2000 |
| 15. Review of UNDAF draft | UNCT | Early November 2000 |
| 16. Final Consolidation | UNDAF Task Force | November 2000 |
| 17. Consultative meetings with partners on draft UNDAF | RC / UNCT / UNDAF Task Force | November 2000 |
| 18. Final drafting | UNCT / UNDAF Task Force | November 2000 |
| 19. Government endorsement | RC | November 2000 |
| 20. Finalisation, clearance & distribution of UNDAF document | UNCT | December 2000 |

### VI.2	Lesotho Development Indicator Tables

- Contextual Indicators

| Demographics | Size of Populationa - Million - |  |
| --- | --- | --- |
|  | 1976 | 1.22 |
|  | 1986 | 1.59 |
|  | 1996 | 1.96 |
|  | Fertility Ratea - Rates - |  |
|  | 1986 | 5.3 |
|  | 1996 | 4.9 |
|  | Life Expectancy at Birtha, b - Years - |  |
|  | 1950-1950 | 38.4 |
|  | 1975-80 | 51.8 |
|  | 2000 | 55 |
| Human Development | Human Development Index - Index - |  |
|  | 1988 | 0.580b |
|  | 1992 | 0.473c |
|  | 1998 | 0.569d |
|  | Human Poverty Indexe - Index - |  |
|  | 1997 | 23.0 |
|  | 1998 | 23.3 |
|  | Gender-related Development Indexe - Index - |  |
|  | 1997 | 0.570 |
|  | 1998 | 0.556 |
| Economy | GNP per Capitaf - 1995 USD - |  |
|  | 1975 | 220 |
|  | 1998 | 486 |
|  | External Debtf - % of GDP - |  |
|  | 1997 | 35 |
|  | Gross Domestic Savingsg - % of GDP - |  |
|  | 1988 | -69.0 |
|  | 1996 | -1.8 |
|  | Public expenditure on community and social services - in % of recurrent expenditures - |  |
|  | 1987/88 | 31.8h |
|  | 1996/97 | 46.0i |
|  | Overseas Development Assistancej - Million USD - |  |
|  | 1983 | 204 |
|  | 1997 | 96 |
|  | Foreign Direct Investmentf - Million USD - |  |
|  | 1987 | 17 |
|  | 1997 | 29 |

Sources: a) BOS (1996), b) UN (1998), c) UNDP (1990), d) UNDP (1995), e) UNDP (2000), f) World Bank (1999), g) World Bank (1998), h) Central Bank of Lesotho (1990), i) Central Bank of Lesotho (1999), j) OECD (1999)
.

- Lesotho’s Follow Up to Global Conferences:

| # Conference Goal | # Target |  | # National Targets | # National Follow Up |  | # Key Indicators |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Income-Poverty |  |  |  |  |  |  |  |  |
| Reduced poverty levels | Proportion in extreme poverty in 1990 reduced by ½ by 2015 (WSSD) |  | Lesotho’s Sixth National Development Plan 91996/7- 1998/9) adopted sustainable human development as its over-arching goal To hasten the pace of human development programme especially in geographically disadvantaged mountain areas | Poverty Reduction Programme was formulated, which produced a Poverty Action Plan. The programme received the commitment of over US$200 million during the Round table Conference (RTC) of November 1997 Poverty Reduction Strategy Paper (PRSP), is being formulated with focus on grassroots level. Taskforce has been formed headed by Ministry of Development Planning to spearhead the process. A draft is expected to be completed by June 2000 |  | Poverty headcount ratioa |  |  |
|  |  |  |  |  |  | - % of population with monthly incomes less than Maloti 80 - |  |  |
|  |  |  |  |  |  | 1990 | 49 |  |
|  |  |  |  |  |  | 1993 | 71 |  |
|  |  |  |  |  |  | 1999 | 68 |  |
|  |  |  |  |  |  | Inequality 1997b |  |  |
|  |  |  |  |  |  | Lowest income quartile |  | 2% |
|  |  |  |  |  |  | Gini-index |  | 57 |
| ## Sources: a) Sechaba (forthc.), b) UNDP (1998), c) OECD (1999) |  |  |  |  |  |  |  |  |
| Food Security and Nutrition |  |  |  |  |  |  |  |  |
| Improved child nutrition | Severe/ moderate malnutrition among children <5 to reach ½ of 1990 level by 2000 (WSSD/ FWCW/WSC/WFS) | To reduce malnutrition amongst under-fives from: 18% to 9% (underweight) 5.7% to 2.8% (wasting) 42% to 21% (stunting) |  |  |  | Child nutritiona |  |  |
|  |  |  |  |  |  | - % of children under-5 that are underweight - |  |  |
|  |  |  |  |  |  | 1976 | 22.0 |  |
|  |  |  |  |  |  | 1993 | 15.8 |  |
|  |  |  |  |  |  | 1996 | 16.0b |  |
|  |  |  |  |  |  | - % of children under-5 that are wasted - |  |  |
|  |  |  |  |  |  | 1976 | 3.4 |  |
|  |  |  |  |  |  | 1993 | 2.4 |  |
|  |  |  |  |  |  | - % of children under-5 that are stunted - |  |  |
|  |  |  |  |  |  | 1976 | 23 |  |
|  |  |  |  |  |  | 1981 | 19 |  |
|  |  |  |  |  |  | 1993 | 33 |  |
| Increased food security | Reduce number of chronically under-nourished by half by 2015 (WFS) | Ensure household food security, with focus on comparative advantage and export-oriented growth while ensuring access to basic foodstuff at free market prices |  |  |  | Iodised saltb - % of households with Consumption of iodised salt - |  |  |
|  |  |  |  |  |  | 1996 | 73 |  |
| Sources: a) Ministry of Health – need to confirm source, except, b) BOS (1998). |  |  |  |  |  |  |  |  |

| # Conference Goal | # Target |  | # National Targets | # National Follow Up |  | # Key Indicators |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Health and Mortality |  |  |  |  |  |  |  |
| Improved health care | Universal accessibility of primary health care (ICPD/WSSD/FWCW) | To improve delivery of basic health services, especially to disadvantaged groups. |  |  | Primary Health Care (PHC) adopted 1979 National Adolescent Health and development programme is being implemented by the Ministry of Health | Primary health care - % population with access to primary health care services - |  |
|  |  |  |  |  |  | 1987 |  |
|  |  |  |  |  |  | 1990 |  |
|  |  |  |  |  |  | 1995 |  |
| Reduction in levels of HIV/AIDS | Universal access to Reproductive Health services and information by 2015 (ICPD) | To reduce HIV/AIDS sero-prevalence by 20% by March 2003 100% coverage of PLWHAs through support and care by March 2003 100% of AIDS orphans to be cared for by March 2003 Spread of HIV/AIDS among 15-49 year-olds reduced form 10% per annum to 5% by March 2003 Behavioural change regarding HIV/AIDS among the general public increased from 5% to 25% by March 2003. |  |  | National AIDS Prevention and Control Programme (NAP) set up in the Ministry of Health and Social Welfare | HIV prevalencea - HIV prevalence rate in % of total adult population - |  |
|  |  |  |  |  |  | 1997 | 8.35 |
|  |  |  |  |  |  | 1998 | 9.8 |
|  |  |  |  |  |  | 1999 | 35.3 |
| Reduced infant mortality | Reduction of IMR by 1/3 of 1990 level and below 35 per 1,000 by 2015 (ICPD/WSSD/WCW/WSC) | To reduce IMR from 85/1,000 to 70/1,000 live births by 2000. |  |  | Target of reducing IMR to 70/1,000 live births by 2000 has been passed. | Infant mortalityc - Deaths per 1,000 births - |  |
|  |  |  |  |  |  | 1986 | 85 |
|  |  |  |  |  |  | 1996 | 55 |
| Reduced child mortality | MR at ages <5 reduced by 2/3 of 1990 level by 2015 (ICPD/WSC) | To reduce under-five mortality rate from 60 to 30 per 1,000 live births |  |  |  | Under 5 mortality - Deaths per 1,000 in age group - |  |
|  |  |  |  |  |  | 1983 | 156d |
|  |  |  |  |  |  | 1996 | 60e |
| ## Sources: a) World Bank (forthc.), b) MOH (1999), c) BOS (1996).d) MOH (1984), eMOH 1996. |  |  |  |  |  |  |  |

| # Conference Goal | # Target |  | # National Targets |  | # National Follow Up | # Key Indicators |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Reproductive Health |  |  |  |  |  |  |  |
| Improved maternal health and reduced maternal mortality | Reduction by ½ of 1990 levels by year 2000 and a further ½ by 2015 (ICPD/ WSSD/ FWCW/WSC) | To reduce maternal mortality from 282 per 100,000 live births to 140 per 100,000 live births. |  |  | Safe Motherhood Initiative launched by MOHSW | Maternal mortalitya - Deaths per 100,000 - |  |
|  |  |  |  |  |  | 1992 | 282 |
|  |  |  |  |  |  | 1997 | 738 |
| Increased access to family planning | Universal access to safe/reliable contraceptive methods (ICPD) | To increase condom usage by 50% per annum |  |  |  | Contraceptive prevalencec - Users in % total- |  |
|  |  |  |  |  |  | 1977 | 8 |
|  |  |  |  |  |  | 1993 | 34.6d |
|  |  |  |  |  |  | 1996 | 23 |
| ## Sources: a MOH (1997), c BOS 1996 except d MOHSW 1993 |  |  |  |  |  |  |  |
| Child health and welfare |  |  |  |  |  |  |  |
| Improved child health | Universal immunization against measles (WSC) |  |  | To maintain and increase high level of immunisation coverage – at least 90% of children under one-year by 2000. |  | Immunisation of one year oldsa, b - Measles, in % of all - |  |
|  |  |  |  |  |  | 1999 | 55 |
|  |  |  |  |  |  | - Total immunisation, in % of all - |  |
|  |  |  |  |  |  | 1993 | 71 |
|  |  |  |  |  |  | 1996 | 67 |
| Reduced child labour | Elimination of child labour (WSSD) |  |  |  | A National Co-ordination Workshop was held in October 1999 to address the herd boy issue and to develop impact-oriented programmes. A 20-member National Steering Committee to deal with herd boys was set up under the chairmanship of the Director of Sectoral Planning at MDP. Programmes focusing on herd boys are to be included in the 7th National Development Plan. | Herd boys c - % of all males 5-19 of age - |  |
|  |  |  |  |  |  | 1997 | 32 |
| ## Sources: a) MOH (1999), b) BOS (1998), c) UNICEF 1999. |  |  |  |  |  |  |  |

| # Conference Goal | # Target | # National Targets |  | # National Follow Up | # Key Indicators |  |
| --- | --- | --- | --- | --- | --- | --- |
| Education |  |  |  |  |  |  |
| Increased access to basic education | Universal access, and completion of primary education by 2015 (EFA/WCW/WSC/ ICPD) |  | To increase primary school enrolment rate from 64 per cent for boys and 76 per cent for girls to 80 per cent for both sexes by 2000. To embark on a programme of Free Primary Education. | Free primary education adopted as effective from January 2000 and starting with Std.1. | Primary school enrolmenta - Enrolment in % of children in school age - |  |
|  |  |  |  |  | 1989 | 77.3 |
|  |  |  |  |  | 1995 | 66.7 |
|  |  |  |  |  | 1998 | 54.8 |
|  |  |  |  |  | Primary Pupil-Teacher ratiob |  |
|  |  |  |  |  | 1983 | 51.1 |
|  |  |  |  |  | 1992 | 51.4 |
|  |  |  |  |  | 1998 | 45.2 |
|  |  |  |  |  | Primary School-Student Ratiob |  |
|  |  |  |  |  | 1983 | 259 |
|  |  |  |  |  | 1992 | 302 |
|  |  |  |  |  | 1998 | 292 |
|  |  |  |  |  | Secondary Teacher-Student Ratiob |  |
|  |  |  |  |  | 1983 | 20.2 |
|  |  |  |  |  | 1992 | 21.2 |
|  |  |  |  |  | 1998 | 23.8 |
|  |  |  |  |  | Secondary School-Student Ratiob |  |
|  |  |  |  |  | 1983 | 255 |
|  |  |  |  |  | 1992 | 279 |
|  |  |  |  |  | 1998 | 348 |
|  |  |  |  |  | Unqualified teachers in Primary Schoolsb - % of total - |  |
|  |  |  |  |  | 1983 | 29.1 |
|  |  |  |  |  | 1992 | 21.0 |
|  |  |  |  |  | 1998 | 21.8 |
| Increased literacy | Adult illiteracy reduced by ½ 1990 level by 2000 (EFA/WSSD/ WCW) |  | To reduce illiteracy rate from 38% to 10% with an emphasis on male literacy. |  | Adult illiteracyc - Basic illiterate in % of total - |  |
|  |  |  |  |  | 1985 | 38 |
|  |  |  |  |  | 1997 | 39 |
|  |  |  |  |  | - Functionally illiterate in % of total - |  |
|  |  |  |  |  | 1985 | 54 |
|  |  |  |  |  | 1997 | 43 |
| ## Sources: a) BOS( 1998), b) Ministry of Education (1984, 1992, 1998), c) Ministry of Education (1985, 2000). |  |  |  |  |  |  |

| # Conference Goal | # Target | # National Targets |  | # National Follow Up | # Key Indicators |  |
| --- | --- | --- | --- | --- | --- | --- |
| Gender Equality and Women’s Empowerment |  |  |  |  |  |  |
| Gender equality in education | Eliminate disparity in primary and secondary education by 2005 (ICPD/WSSD/ FWCW) |  | Equal opportunity in education to be enforced by national law | The Ministry of Environment, Gender, and Youth Affairs was created in 1998. A National Gender Policy is being drafted but is yet to be finalised. | Ratio of boys to girls in secondary educationa |  |
|  |  |  |  |  | 1983 | 1.5 |
|  |  |  |  |  | 1991 | 1.45 |
|  |  |  |  |  | 1998 | 1.4 |
|  |  |  |  |  | Female illiteracyb - Basic illiterate in % of total - |  |
|  |  |  |  |  | 1985 | 30 |
|  |  |  |  |  | 1997 | 37 |
|  |  |  |  |  | - Functionally illiterate in % of total - |  |
|  |  |  |  |  | 1985 | 47 |
|  |  |  |  |  | 1997 | 42 |
| Gender equality in employment | Eliminate discriminatory practices in employment (FWCW) |  | Measures to be put in place against discrimination, exclusion or restriction on the basis of sex | Law Reform Commission established in 1997 to review and revise all laws which discriminate against women | Economically active womenc - % of total economically active population- |  |
|  |  |  |  |  | 1986 | 27 |
|  |  |  |  |  | 1996 | 33.5 |
| Women’s political empowerment | Equitable access to political institutions (FWCW) |  |  | Although the legal system does not prohibit women from holding public office, there is no quota system in place in Lesotho. | Female Government Ministers - % of total - |  |
|  |  |  |  |  | 2000 | 6 |
|  |  |  |  |  | Female Principal Secretaries - % of total - |  |
|  |  |  |  |  | 2000 | 19 |
| Sources: a) Ministry of Education (1984, 1992, 1998), b)b Ministry of Education (1985, 2000), c) BOS (1996). |  |  |  |  |  |  |

| # Conference Goal | # Target | # National Targets |  | # National Follow Up | # Key Indicators |  |
| --- | --- | --- | --- | --- | --- | --- |
| Housing and Basic Household Amenities and Facilities |  |  |  |  |  |  |
| Adequate shelter for all | Provision of sufficient living space and avoidance of overcrowding (HABITAT II) |  | To develop and adopt a National Shelter policy. To reduce national average household size from 5 persons per house, and to increase average number of rooms per house from 2 to 3. | The Ministry is in the final phase of developing a National Shelter policy. A Land Commission is presently reviewing the 1979 Land Act, which is expected to bring about the equitable enforcement of a legal and regulatory framework for land use | Households sizesa - average number of inhabitants - |  |
|  |  |  |  |  |  | 5.0 |
|  |  |  |  |  | 1986 | 5.1 |
|  |  |  |  |  | 1996 | 5.0 |
|  |  |  |  |  | - Houses with 5 rooms or more, in % of total - |  |
|  |  |  |  |  | 1996 | 10.7 |
|  |  |  |  |  | - houses, with 1 room in % of total - |  |
|  |  |  |  |  | 1996 | 33.4 |
| Improved access to safe drinking water | Universal access to safe drinking water; full coverage of drinking water supply (by 2025). (WCW/WSSD/UNCED) |  | To increase access to safe water from 55 per cent to 82 per cent in rural areas and from 58 per cent to 80 per cent in urban areas by 2000. | The target set for urban areas has been achieved but the rural figure falls considerably short of the 82 per cent target. | Safe waterb - National access in % of total - |  |
|  |  |  |  |  | 1996 | 62 |
|  |  |  |  |  | - Rural population with access, in % of total - |  |
|  |  |  |  |  | 1993 | 55 |
|  |  |  |  |  | 1996 | 57 |
|  |  |  |  |  | - Urban population with access, in % of total - |  |
|  |  |  |  |  | 1993 | 58 |
|  |  |  |  |  | 1996 | 91 |
| Improved access to safe sanitation | Universal sanitary waste disposal (WCW/WCS/WSSD/ UNCED) |  | To increase access to latrines from 35 per cent to 65 per cent in rural areas and from 38 per cent to 60 per cent in urban areas by 2000. | Progress has been made towards the attainment of the 2000 goal of 60 pre cent in urban areas, but no improvement has been made in rural areas. | Safe sanitationb - National access in % of total - |  |
|  |  |  |  |  | 1996 | 45 |
|  |  |  |  |  | - Rural population with access, in % of total - |  |
|  |  |  |  |  | 1993 | 35 |
|  |  |  |  |  | 1996 | 35 |
|  |  |  |  |  | - Urban population with access, in % of total - |  |
|  |  |  |  |  | 1993 | 38 |
|  |  |  |  |  | 1996 | 56 |
| Sources: a) BOS(1996), b) BOS (1998). |  |  |  |  |  |  |

| # Conference Goal | # Target |  | # National Targets | # National Follow Up | # Key Indicators |  |
| --- | --- | --- | --- | --- | --- | --- |
| Environment |  |  |  |  |  |  |
| Improved environment | Clean and healthy environment and reversal of current trends in loss of environmental resources (UNCED) | To ensure that environmental concerns are integrated into all aspects of life in Lesotho. To prepare a National Environment Action Plan. To establish a national institutional framework to implement Agenda 21 and the UNCED Process |  | First comprehensive National Environment Action Plan was produced in 1998. National Environment Secretariat was established in 1994 and a fully-fledged Ministry of the Environment set up in September 1998. Since 1998 NES has held a series of workshops aiming at bringing environmental issues into both formal and non-formal education. The campaign is on-going. Draft Environmental Law is under discussion in Parliament. | Carbon Dioxidea - Emissions per capita, tonnes - |  |
|  |  |  |  |  | 1994 | 0.97 |
|  |  |  |  |  | 1997 | 2.55 |
|  |  |  |  |  | Biodiversitya - Total protected land area, ha. - |  |
|  |  |  |  |  | 1997 | 197,378 |
|  |  |  |  |  | Landless householdsa - Landless rural households on % of total - |  |
|  |  |  |  |  | 1970 | 13 |
|  |  |  |  |  | 1980 | 22 |
|  |  |  |  |  | 1990 | 55 |
|  |  |  |  |  | Arable Landa, b - % of total land area - |  |
|  |  |  |  |  | 1997 | 9 |
|  |  |  |  |  | - Arable land per capita, ha - |  |
|  |  |  |  |  | 1992 | 0.169 |
|  |  |  |  |  | 1996 | 0.150 |
|  |  |  |  |  | Energya - % of national demands met by traditional fuels - |  |
|  |  |  |  |  | 1997 | 76 |
| Sources: a) Ministry of Environment, Gender and Youth Affairs (1998), b) BOS (1996). |  |  |  |  |  |  |

| Employment and Sustainable Livelihood (b) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Creation of full employment | Universal access to paid employment (WSSD) | To formulate policies to combat poverty, high unemployment, declining social services and promote equitable income distribution. |  | Unemploymentb - % of economically active population - |  |
|  |  |  |  | 1976 | 5.7 |
|  |  |  |  | 1986 | 7.0 |
|  |  |  |  | 1996 | 23.5 |
|  |  |  |  | 1997 | 34.5b |
| Source: a) BOS 1996, b) Ministry of Labour and Bureau of Statistics (1998) |  |  |  |  |  |

3. Conference and Convention Indicators on Governance and Civil and Political Rights

| ###### Conference Goal | ###### Target | ###### Indicators |
| --- | --- | --- |
| International Legal Commitments for Human Rights |  |  |
| Universal ratification of international human rights instruments | Acceding to all international human rights instruments and avoiding the resort to reservations, as far as possible | Lesotho has ratified: - International covenant on economic, social and cultural rights (1992), - International covenant on civil and political rights (1992), - International convention on the elimination of all forms of racial discrimination (1971), - Convention on the prevention and punishment of the crime of genocide - Convention on the rights of the child (1992), - Convention on the elimination of all forms of discrimination against women (1995), with reservations, - Convention relating to the status of refugees. |
| Democracy and Participation |  |  |
| Strengthened democratic institutions and popular participation | Free and fair elections and democratic government (WCHR) | - Democratic elections are held every 5 years. - Lesotho’s Constitution contains the Bill of Rights to ensure that the right to freedom of expression, association and assembly are recognised. Press freedom is promoted but there is no media policy as such. The Bill of rights is modelled on the Universal Declaration of Human Rights. |

| ###### Conference Goal | ###### Target | ###### Indicators |
| --- | --- | --- |
| Administration of Justice |  |  |
| Fair administration of justice | Effective legislative framework, law enforcement, prosecutions, legal profession, and fair trials in conformity with international standards (WCHR) | - It has been alleged that the Government and Chieftainship have some influence on Magistrates (US Dept of State, Lesotho Country Report on Human Rights Practices, 1998). Judges have also been accused of conservatism. |
| Improved framework of remedies | Existence of legal remedies in conformity with international standards | - The Office of the Ombudsman protects the rights of individuals who believe themselves to be victims of unjust acts on the part of the public administration. - The Office of the Ombudsman focuses on responding to individual complaints concerning abuse of power and maladministration by public officials of Government and Parastatals. |
| Security of Person |  |  |
| Liberty and security of person | Elimination of gross violations of human rights affecting security of person, including torture and cruel, inhumane or degrading treatment or punishment; summary and arbitrary execution; disappearances, and slavery (WCHR) | - Lesotho’s Constitution prohibits torture and other cruel, inhumane and degrading treatment or punishment. |

# SECTION VII: REFERENCES

Bureau of Statistics. 1968. 1967/68 Rural Household Consumption and Expenditure Report Survey. Maseru.

__________. 1981. Lesotho Fertility Survey 1977, First Report: Vol. II. Maseru.

__________. 1996a. Population Census Analytical Report, Volume IIIA: Population Dynamics. Maseru.

__________.  1996b. Population Census Analytical Report, Volume IIIB: Socio-Economic Characteristics and Population Projections. Maseru.

__________. 1999. Statistical Report No.6. Maseru.

Bureau of Statistics/Ministry of Labour and Employment. 1998. Labour Force Survey 1997. Maseru.

Bureau of Statistics/UNICEF. 1998. Exposing Geographic Inequality: Lesotho’s Multiple Indicator Cluster Survey. A District Level Report. Maseru.

Central Bank of Lesotho. 1990. Annual Report, 1989. Maseru.

__________. 1999. Annual Report, 1998. Maseru.

Economist Intelligence Unit. 1999. Country Profile Lesotho: 1998-99. London.

Government of Lesotho. 1993. The Constitution of Lesotho. Maseru.

__________. 1996. Pathway out of Poverty: An Action Plan for Lesotho. Maseru.

__________. 1997. Eighth Round Table Conference: Poverty Reduction Within the Context of Good Governance. Maseru.

__________. 2000. Framework for the Development of Vision 2020. Maseru.

Lesotho Distance Teaching Centre, Ministry of Education.  1985. Adult Literacy in Lesotho, Part I: Results of Reading, Writing and Arithmetic Skills. Maseru.

__________. 2000. National Literacy Survey in Lesotho: Final Report. Maseru.

Lesotho National Early Warning Unit, 2000. Monthly Update January 2000: Issue No.1. Maseru.

__________. 2000. Monthly Update February 2000: Issue No. 2. Maseru.

Lesotho Tourist Board. 2000. Annual Report 1998/1999. Maseru.

Maw, M. A. for Ministry of Health and Social Welfare, Disease Control and Environment Health Division. 1998. Update on AIDS in Lesotho. Maseru.

_________. 1999. AIDS Epidemiology in Lesotho 1999. Maseru.

Ministry of Economic Planning. 1997. Sixth National Development Plan 1996/97 – 1998/99. Maseru.

Ministry of Education, Education Statistics Unit. 1986. Education Statistics 1984. Maseru.

__________. Planning Unit. 1992. Education Statistics 1992. Maseru.

__________. 1998. Education Statistics 1998. Maseru.

Ministry of Environment, Gender and Youth Affairs, National Environment Secretariat. 1999. State of Environment in Lesotho 1997. Maseru.

Ministry of Finance. 2000. Consolidating Democracy, Helping the Poor while laying the Basis for Strong Economic Growth: Budget Speech for the Fiscal Year 2000/20001. Maseru.

Ministry of Health. 1982. Report on a Joint Mission to Evaluate the Lesotho Expanded Programme on Immunisation. Maseru.

__________. 1984. Report of a Joint Evaluation of Primary Health Care in the Kingdom of Lesotho. Maseru.

__________. 1996. Sectoral Round Table Consultations: Health, Building Partnership for the Lesotho Health Sector Reform. Maseru.

Ministry of Health and Social Welfare, Family Health Division. 1993. Report for the International Evaluation Survey on ARI/ CDD/ EPI/ MHC/ FP. Maseru.

__________ /UN Theme Group on HIV/AIDS. 2000. Lesotho Hospital-Based HIV Seroprevalence Survey: Draft Report. Maseru.

Ministry of Justice and Human Rights. 1999. Draft Report on CEDAW. Maseru.

Ministry of Water, Energy and Mining. 1988. Lesotho Energy Master Plan Vol. I Part 2: Energy Resources and Technology Assessment. Maseru.

Mokhosi, E. B. et al. 1999. The Situation and Needs Analysis Survey of Herdboys in Lesotho. Maseru.

National AIDS Programme of Lesotho. 2000. Draft National AIDS Strategic Plan 2000-2003. Maseru.

OECD. 2000. The DAC Journal Development Co-operation 1999 Report: Volume 1, No. 1. Paris.

__________. Development Assistance Committee Database available at

http://www.oecd.org/scripts/cde/viewbase.idc?dbname=cde_dac.

Petersson, L. 1994. Lesotho’s Policy Options and Integration in the Region. Stockholm.

Privatisation Unit. 2000. Lesotho Privatisation and Private Sector Development Project: Fourth Annual Report, 1 April 1999 to 31 March 2000. Masreu.

SADC Commission of Enquiry. September 1998. The Langa Report. Johannesburg.

Southern African Development Community / Southern African Research and Documentation Centre. 1999. SADC Gender Monitor: Monitoring Implementation of the Beijing Commitments by SADC Member States. Harare.

SADC/UNDP/Southern African political Economy Series. 1998. SADC Regional Human Development Report 1998. Harare.

Sechaba Consultants. 1994. Poverty in Lesotho 1994: A Mapping Exercise. Maseru.

__________. Forthcoming. Poverty in Lesotho 1999: More than a Poverty Mapping Exercise.

__________ for UNICEF. 1999. Situation Update of Children and Women in Lesotho. Maseru.

United Nations. 1992. Rio Declaration on Environment and Development. New York.

__________. 1995. Report of the World Summit for Social Development. New York.

United Nations Centre for Human Rights. 1995. National Human Rights Institutions, Professional Training Series No. 4. New York and Geneva.

UNCT, 2000. United Nations Common Country Assessment for Lesotho. Maseru.

United Nations Department of Economic and Social Affairs, Population Division. 1999. World Population Prospects, The 1998 Revision, Volume I: Comprehensive Tables. New York.

United Nations Department of Public Information. 1996. Platform for Action and the Beijing Declaration. New York.

United Nations High Commissioner for Human Rights. 1990. Convention on the Rights of the Child. Geneva.

__________. 1996. Centre for Human Rights Report of the Needs Assessment Mission to Lesotho, 9-17 December 1996. New York.

UNDP. 1990. Human Development Report. New York.

__________. 1995. Human Development Report 1995. New York.

__________. 1998. National Human Development Report Lesotho. Maseru.

__________. 1999. Human Development Report 1999. New York.

__________. 2000. Human Development Report 2000. New York.

__________. 2000. Poverty Report 2000: Overcoming Human Poverty. New York.

UNU and UNDP World Income Inequality Database available at http://www.wider.unv.edu/wiid/ wiiddoc.htm.

UNESCO. 1983. The Statistics of Education Attainment and Literacy in 1970-1980. Paris.

UNICEF. 1997. Lesotho 1997 Annual Report. Maseru.

__________. 1998. Annual Report Lesotho 1998. Maseru.

United States Bureau of the Census. 1999. World Population Profile: 1998. USA.

Wereko, T. B. 1997. Brain Drain in Lesotho. Maseru.

World Bank. 1995. Lesotho Poverty Assessment. Washington.

__________. 1998. African Development Indicators 1998/99. Washington.

__________. 1999a. 1999 World Development Indicators. Washington.

__________. 1999b. Lesotho Hospital Based HIV Seroprevalence Survey October – November 1999: Revised HIV Prevalence Estimates Draft I. Washington.

__________. 2000. Poverty Reduction Strategy Papers Internal Guidance Note. Washington.