Annual session, 2004

Date, Geneva

Item x of the provisional agenda

UNDP

UNDP: COUNTRY PROGRAMMING AND RELATED MATTERS

COUNTRY PROGRAMME DOCUMENT FOR REPUBLIC OF MAURITIUS 2005-2007

CONTENTS

|  |  | Paragraphs | Page |
| --- | --- | --- | --- |
| Introduction |  |  | 2 |
| - Situation Analysis |  | 1-7 | 2 |
| - Past cooperation and lessons learned |  | 8-10 | 3 |
| - Proposed programme |  | 11-17 | 3 |
| - Linkage with the Common Country Assessment and MDGs |  | 11 | 3 |
| - Intended results |  | 12-15 | 3 |
| - Cooperation strategies |  | 16-17 | 4 |
| - Programme management, monitoring and evaluation |  | 18-23 | 5 |
| - Monitoring |  | 18-19 | 5 |
| - Execution and implementation |  | 20 | 5 |
| - Resource mobilization |  | 21-22 | 5 |
| - Country office structure and staffing |  | 23 | 6 |
| Annexes |  |  |  |
| Annex I: The results and resources framework for 2005-2007 |  |  | 7 |
| Annex II: Resource Mobilization Table for Mauritius (2005-2007) |  |  | 11 |
| Annex III: Glossary |  |  | 12 |

Introduction

The formulation of the current Country Programme 2005 – 2007 for Mauritius was led jointly by the Government of Mauritius and the UNDP Country Office with the active participation of donors, resident UN agencies, parastatal and autonomous bodies, civil society organizations, NGOs and the private sector. The consultative process of the programme formulation, anchored in a human rights-based approach favoring substantial engagement of the citizens, was guided by the second multi-year funding framework (MYFF) for the period 2004-2007, the CCA (November 2003), the National Poverty Action Plan 2001, the MDG Status Report 2002 (Mauritius) and the sub-national Report for Rodrigues (2003), the National Gender Action Plan, and the National Budget of 2000 which outlined the government economic agenda, national vision and priorities. The programme focuses on some of the development priority areas identified mainly in the CCA and MDG status report, consistent with national priorities. Mauritius became a category C country in January 2004 following the closure of UNICEF and UNFPA Offices on 31 December 2003 resulting in only two resident UN agencies (WHO, UNDP), and therefore preparation of an UNDAF is not required.  As a middle-income country, Mauritius does not have a PRSP. The programming period aligns with the second MYFF 2004-2007.

I. 	Situation Analysis

1.	The Republic of Mauritius has experienced an average annual GDP growth of 5.5 percent over the past 2 decades. Per capita income has tripled to USD 3,890 and extreme poverty has fallen significantly for mainland Mauritius to 9.7 percent. These gains were accomplished through foreign aid, political stability, sound fiscal management, export promotion, preferential trade agreements, support of private sector, FDI inflows, and a social welfare state. However, at the turn of the millennium, Mauritius is undergoing structural transformation, moving from a predominantly sugar production and textile manufacturing into a service and knowledge intensive economy as ODA flows and FDI are falling, while preferential trade agreements are being phased out. This is happening at a time when growth rate of the economy is lower than historical averages partly due to lower FDI and an uncertain international environment, leading to critical reforms in the approach to welfare spending and a major risk of erosion of past gains in social development.

2.	 The island of Rodrigues, however, has not benefited appropriately from these gains and poverty levels stand at 37.6 percent in the small population of around 36,000 inhabitants despite several national poverty alleviation programmes being implemented by the Government and several donors. In 2002, the Government of Mauritius voted the Rodrigues Regional Assembly Bill to provide more political and economic autonomy and allow Rodriguans to chart out their own sustainable development priorities. The utmost priority is to reduce poverty level and to fully integrate Rodriguan  development with the main growth centres on mainland Mauritius through participatory development of  home-based sustainable development strategies suited to the local context. (http://un.intnet.mu/UNDP/html/pub.htm). http://economicdevelopment.gov.mu/pov.htm)

3. 	A second major challenge for Mauritius during the programming period relates to containing or reversing the upward rise in unemployment, especially among youth, unskilled women or women headed households in general, while implementing the critical reforms and economic transformation, as these two groups constitute over 70 percent of all unemployed in Mauritius. As Mauritius moves into the knowledge-intensive economy, with the development of the ICT sector and the vision of turning Mauritius into a cyber-island, there is a real risk of exacerbating the current skills mismatch especially among women, unless educational reforms are implemented to cater for new exigencies of the labor market.  To note that Mauritius has already achieved MDG Goal 2 on achieving universal primary education and Goal 3 on ensuring equal access to education.  Despite these gains, opportunities for vulnerable groups must be reinforced.

4. 	Despite government focus on reducing remaining gender disparities in the labour market, in political representation and empowerment, challenges still remain, as reflected in the Gender Action Plan (2000) (http://women.gov.mu/gender_bureau.htm) and the MDG target for gender in the Mauritius MDG report 2002 (http://un.intnet.mu/UNDP/html/pub.htm). Most recently, the Action Plan for Engendering the National Budget (2003) was developed with a view to working towards more gender equality in economic policy-making and national budgeting exercise in the coming years.

5. 	Thirdly, as a small island developing state, Mauritius faces all the inherent vulnerabilities of SIDS in pursuing sustainable development. With a limited land area, further economic development is a constant balancing act between preserving the state of the terrestrial and marine environment on the one hand and further development of economic sectors such as tourism, agriculture and industries on the other hand. This vision is well articulated in the National Environmental Strategies (NES) for the Republic of Mauritius and the National Environmental Action Plan (NEAP) II published in 1999, which are the blueprints for the sustainable development of Mauritius. The lynchpin of this strategy centres on (a) conservation of marine biodiversity; (b) management and disposal of liquid and solid wastes, in particular hazardous substances; (c) land management; and (d) energy efficiency and conservation (http://un.intnet.mu/UNDP/html/pub.htm).  Mauritius will be hosting the Global Conference for the review of the Barbados Plan of Action for SIDS in 2005.

6. 	The promotion of good governance remains a priority for the country as Mauritius embarked on a systematic fight against corruption in all spheres of economic activity. By recognizing that corruption can impact significantly on economic development, the present administration has voted bold legislation and established the Independent Commission against Corruption (ICAC in 2002), under the aegis of the Prime Minister’s Office, to deal with all aspects of corruption and money laundering.

7.	In line with the National Strategic HIV/AIDS Plan 2001-2005, Government leadership to prevent and halt the spread of HIV/AIDS in Mauritius, particularly among at risk groups, is strong, as is the commitment to provide care and support for those affected and infected by the disease.  UNDP will support Government efforts where necessary.

8. 	As the country moves into a knowledge-based economy, focusing on ICT services, capacity to formulate, coordinate, monitor and evaluate development programmes by all stakeholders will need to be strengthened, especially for civil society organizations, in order to increase their effective participation as an important stakeholder in their country’s development.

II. 	Past Cooperation and Lessons Learned

9.	The Country Programme Review (2003) noted positive key results under the following areas: a) good governance - an investment policy review for attracting Foreign Direct investment (FDI) to Mauritius and a review of the fiscal incentive regime carried out, setting-up of the Office of the Director of Court Services to improve administration of justice; b) poverty alleviation – capacity-building in participatory approach techniques and community development, in management of micro-enterprises and micro-credit as well as in productive techniques and promotion of a local economic development network in Rodrigues Island, a national MDG report for Mauritius and sub-national MDG report for Rodrigues finalized; c) environment protection - a sustainable environmental management plan for an industrial estate (cluster of manufacturing enterprises) adopted, which will serve as a pilot for replication to other industrial estates in Mauritius, an ‘ electrification feasibility report’ and a ‘biomass based steam cycle power generation for Agalega Islands’ formulated; a portfolio of GEF projects developed for implementation under CP 2005-2007 and d) gender equality – the adoption of an action plan for engendering the national budget and a time use survey carried out.

10.	Notable lessons learned from previous cooperation strategies include: (a) interventions being more catalytic and upstream, (b) an increased use of the NEX modality, (c) whenever local capacity exists, priority being given to local expertise, (d) monitoring, evaluation, sustainability and exit strategies being an integral part of project design and implementation and e) increase in the use of UNDP knowledge networks.

11.	Other significant lessons learned suggest strongly that capacity building on NEX should be maintained particularly for NGOs and civil society.

- Proposed Programme

A. Linkage with the Common Country Assessment (CCA) and MDGs.

12.	Given the limited TRAC resources, the new Country Programme focuses on the priority areas of intervention identified in the CCA and the shortcomings in the MDG status report for Mauritius and the sub-national report for Rodrigues. The strategy is guided by national development priorities, the comparative advantage of UNDP in the area of poverty alleviation, gender empowerment and environmental protection, as well as available resources, and resource mobilization potential from the Global Environment Facility (GEF), trust funds and other partnership potentials to achieve the MDG targets, fostering good governance and building capacity (http://un.intnet.mu/UNDP/html/pub.htm).

B.  Intended Results

13. 	Objective 1 – Fostering an enabling environment for policy and decision-making in order to achieve the MDGs:  i) UNDP will pursue the formulation and support the implementation of a Sustainable Integrated Development Plan for Rodrigues Island with a view to achieving the MDG targets under the overarching umbrella of poverty reduction; ii) UNDP will also support mechanisms that will help address the weak gender environment to achieve the MDG goal on gender equality and empowerment of women; iii) As for the Civil Society, a policy, institutional and regulatory framework will be elaborated in order to build capacity and foster more accountability amongst NGOs/CBOs; iv) UNDP will support the formulation and implementation of a National ICT Strategy and capacity building for IT incubators; and v) UNDP will be catalytic in promoting good governance through its support to build capacity of the Independent Commission against Corruption, under the Prime Minister’s Office, through sharing of best practices.

14. 	Objective 2 – Promotion and protection of the environment and energy: In keeping with GEFs windows, and on the basis of priorities and needs identified by all national actors, the emphasis here will be on upstream policy advice through the following i) the removal of barriers to energy efficiency and energy conservation in buildings, ii) capacity building for sustainable land management and iii) partnerships for environmental sustainability of marine protected areas UNDP’s core resources will be invested in a strategy development for sustainable management and disposal of hazardous substances in a small island context.

15. 	Clear linkages exist between the two mentioned objectives and their respective outcomes:

- The formulation and the implementation of a sustainable integrated development plan for Rodrigues island (SIDPR) will be reinforced by the capacity-building for sustainable land management and the co-management of marine protected areas in Mauritius. The SIDPR will also build on the promotion of gender equality and the strengthening of CSOs in the Republic of Mauritius.

- Gender mainstreaming and civil society empowerment will be further interlinked in their respective projects.

- Energy and environment outcome targets will be reinforced through the capacity building of the Civil Society in development projects.

16. 	The outcomes towards which UNDP will make a significant contribution and the outputs to be achieved are shown in the Results and Resources Framework for 2005-2007 (Annex I).

C.  Cooperation Strategies

17.	In a context of falling ODA flows and dwindling TRAC allocations, UNDP will seek alliances with several development actors and donors with a view to combine resources and to generate an optimal development impact. Thus building on the results of discussions held during the preparation of the proposed programme as well as on its past collaboration with partners, UNDP intends to enter in a partnership with:

- UN system: Collaboration with UN agencies would include: i) FAO for sustainable land management, ii) ILO for implementation of ILO Conventions 100 (equal remuneration for men and women workers for work of equal value) and 111 (non-discrimination in respect of employment and occupation) and iii) UNIFEM for gender-responsive budgeting. UN agencies together with UNDP would contribute to the formulation and the implementation of the Sustainable Integrated Development Plan for Rodrigues (SIDPR).

- World Bank: the focus would be on financial and technical assistance in gender responsive budgeting with line ministries, but also support to the implementation of the Sustainable Integrated Development Plan for Rodrigues Island. The Bank’s Information for Development Program (infoDev) would be approached for support to capacity building for IT incubators

- African Development Bank (AfDB):  strategic partnerships would be forged with the ADB for support to regional initiatives such as i) an Africa Regional ICT Institute under the patronage of the NEPAD ICT sector and ii) support to regional HIV/AIDS initiatives. UNDP would also partner with the AfDB’s study on the links between social exclusion, gender and poverty in Mauritius and implications for future interventions.

- Bilaterals: consultations with selected bilaterals in areas of common interest, such as with CIDA on land degradation would be further explored.

- Multilaterals: Building essentially on the partnerships forged during the previous programme, UNDP would continue to cooperate with i) the European Union in the area of civil society empowerment and with ii) the Commonwealth Secretariat in the area of gender.

- Civil Society:  There would be an intensified effort to build collaborative relationships with NGOs at national level centred on: (a) the development of a framework for regulatory processes (accountability), (b) formulation, monitoring and evaluation of development programmes and c) capacity development of institutions.

- Private sector: financial and technical collaboration will be sought with the private sector in the areas of sustainable land management (private landowners); energy efficiency and conservation (building developers), management of MPAs (hotel industry) and the management and disposal of used batteries (manufacturing). Strategic alliances will be forged with Government for the implementation of ILO Conventions 100 and 111 as well as for the implementation of the SIDPR in Rodrigues island.

- South-south cooperation:  would be further explored with anti-corruption institutions with a view to building on international best practices for the strengthening of the capacity of the Independent Commission against Corruption (ICAC) in Mauritius.

18.	In view of the strong focus on policy support and capacity building, partnership strategies will be implemented along the following lines:

- Strengthening or creation of capacity of institutions and human resources throughout public sector and civil society through local and overseas training and tapping into international expertise

- Substantial investment in processes of coordination, monitoring and evaluation of programmes and projects development through local networking, local training and transfer of knowledge

- Providing access to good practices through the UNDP’s global knowledge network and the Sub-regional Resource Facility (SURF) as well as through South-South and other types of cooperation.

IV. 	Programme Management, Monitoring and Evaluation

A.  Monitoring

19.	Outcome indicators, including associated baselines and targets have been agreed with the Government in line with the results-based management (RBM) policy of UNDP (see Annex I).

20.	UNDP will work closely with implementation partners to ensure that basic project monitoring and evaluation systems are in place and aligned with the results framework. Quarterly Programme Steering Committee meetings will be held with the coordinating Ministry.

- Execution and Implementation

21. 	As recommended in the Country Programme Review (2003), national execution will remain the preferred modality.  In addition:

- NEX training for implementation partners will consolidate programme delivery, effectiveness and efficiency.

- The United Nations Volunteers programme will be called in to support the execution of UNDP programmes/projects whereas the United Nations International Short-Term Advisory Resources (UNISTAR) will fill in when specific technical capacity is not locally available.

- UNDP will continue - along its legal framework and procedures - to provide project support services at the request of the Government, in areas such as recruitment, contracting and procurement of goods and services, against payment of appropriate fees in accordance with the UNDP policy on cost recovery.

C.  Resource Mobilization

22.	The resource mobilization strategy will be revised and will evolve around two pillars: 1) catalytic interventions in specific strategic areas that are also most likely to attract partnerships and 2) UNDP’s proven advantage in resource mobilization in environment and energy sectors, where funding has already been forthcoming. As for the first pillar, core resources will be used as seed money to obtain the commitment from other donors as well as at the same time engaging them in detailed programme development. A Round Table will be organized for Rodrigues – in conjunction with the Ministry of Finance and Economic Development, the Ministry of Rodrigues and Rodrigues Regional Assembly for mobilizing funds for the implementation of the Sustainable Integrated Development Plan. Assistance will be provided for the formulation of a national ICT strategy reflecting the country’s vision in this emerging growth sector. As for the second pillar, UNDP will continue to capitalise on the non-core funding available from the Global Environment Facility, the GEF Small Grants Programme (GEF/SGP) and the UNDP Thematic Trust Funds. Last but not least, UNDP will systematically aim for a 1:1 cost-sharing ratio from partners, including government cost-sharing. Throughout, UNDP will be promoting its activities through the media and engage in on-going interaction and reporting with donors.

23.	 UNDP expects to generate approximately $ 2 million from the Global Environment Facility, and at least $ 3 million from government on a cost-sharing basis, including Government cash contributions. The contribution from Government will also comprise imputed costs. Support from other partners will also be sought on a cost-sharing basis or through parallel funding.

D.  Country Office Structure and Staffing

24.	The Country Office capacity will be strengthened – as appropriate – in accordance with the resources mobilized.

The fact that many core posts had been cut during the last re-profiling exercise, has resulted in a work overload for the remaining staff. Therefore, it is hoped that the new Enterprise Resource Planning (ERP) software (Atlas) will improve Country Office efficiency and that the continued effort in resource mobilization will enable the Country Office to recruit the required additional non-core staff.

Annex I: The Results and Resources Framework for 2005-2007

| Objective 1: | Fostering an enabling environment for policy and decision-making in order to achieve the MDGs. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Programme Component and Service Lines | Country programme outcomes, including outcome indicators | Country programme outputs | Output indicators | Role of partners | Indicative Resources (‘000 USD) (by source of funds) |  |
| Goal 1: Achieving the MDGs and reducing human poverty |  |  |  |  |  |  |
| SL1.2: Pro-poor policy reform to achieve MDG targets | A sustainable and integrated development and management for Rodrigues Island, contributing to employment creation, poverty reduction, and the sustainable use and conservation of environmental and natural resources Indicators: A strategy with a short-term action plan for priority development activities over the next 5 years contributing to the MDG targets set for 2015; Poverty incidence in Rodrigues target 30% by end 2007 (baseline: 37.6%); Employment creation: unemployment in Rodrigues target 10% by end 2007 (baseline: 13.01%); Proportion of land covered by forest (soil erosion) target 40% (baseline: 34% in 2003) | - A Sustainable Integrated Development Plan for Rodrigues (SIDPR) formulated and capacity built of the Economic Planning and Monitoring Unit (EPMU) for follow-up to implementation of the SIDPR and MDG monitoring - Priority actions identified and implemented for employment creation to reduce poverty - Priority actions identified and implemented for the sustainable use and conservation of environmental and natural resources | - A Sustainable Integrated Development Plan for Rodrigues available by June 2005 (Baseline: no separate Development Plan for Rodrigues) and capacity built of at least two officials of the EPMU for the implementation of the SIDPR and MDG monitoring by March 2005 (Baseline: EPMU not operational) - Capacity built in identified development priorities for creation of employment by end 2007 (Baseline: not yet started) - Capacity built in identified development priorities for environment/natural resources by end 2007 (Baseline: not yet started) | The Rodrigues Regional Assembly (RRA) will take a leading role in the formulation and the implementation of the SIDPR, in collaboration with the Government of Mauritius, the UNDP and other UN agencies. A Round Table will be organized by the RRA in order to obtain financial support from other donors for the implementation of the same. The CSO, in particular the Rodrigues Council of Social Services (RCSS, especially the Village Committees) and the Private Sector will contribute to the consultations during the SIDPR formulation process. Support to the formulation and the implementation of the SIDPR will be explored with EU, WB, AfDB and other donors. | Regular TRAC 300 Other CS 400 |  |
|  |  |  |  | Sub-Total | 700 |  |
| SL1.6: Gender Mainstreaming | Gender equality promoted through advocacy of MDG targets, International Covenants and UN Conventions (CEDAW) and women empowered through the setting-up of financial, economic, analytical and legal mechanisms Indicators: The MDG indicators for gender equality achieved by 2007 (MDG Indicator 12: Proportion of seats held by women in National Parliament will be 15%); Gender-responsive budget allocations in all ministries operational by end 2007; Remuneration orders and Labour Act revised and operational for equal remuneration for men and women workers for work of equal value | - The Gender-Responsive Budgeting (GRB) Action Plan implemented - Capacity developed for gender-sensitive analysis - An enabling environment established and capacities built - at national level - for implementation of ILO Convention 100 (equal remuneration for men and women workers for work of equal value) - A National Gender Policy developed and appropriate mechanisms devised to promote empowerment of women | - A GRB Team established, budget analyses of ministries available and consultations held with Parliamentarians, NGOs, Unions and Academia during Phase 2 of the Action Plan on GRB by end 2005, (Baseline: GRB Action Plan approved by Cabinet on 1 November 2003, implementation starts mid-2004, GRB Team not yet operational) - Time Use Survey findings and implications on decision-making available and published by mid 2005 (Baseline: a first Time Use survey in process) and a Gender Information System (GIS) operational by end 2007 - Remuneration orders revised, an increase in participation (30%) of women in Trade Unions, capacities in negotiating techniques built by end 2007 (Baseline: ILO Convention 100 signed) - A National Gender Policy available and a National Gender Mechanism developed (NGM) by end 2006 (Baseline: White Paper) | The Ministry of Women will take the leading role in the implementation of the GRB Action Plan, in collaboration with the UNDP and the Commonwealth Secretariat. UNIFEM will be consulted for further technical support. Parliamentarians, NGOs, Unions and Academia will be consulted and sensitized on the GRB process to guarantee its sustainability and critical mass built-up within the Mauritian society. As for the gender-sensitive analytical mechanisms, the Ministry of Women in collaboration with the Central Statistics Office and the UNDP will promote the importance of the Time Use survey findings and their use in decision-making as well as the Gender Information System. The Ministry of Women jointly with the Ministry of Labour will take the responsibility to implement ILO Convention 100 in partnership with the UNDP, ILO, the Private Sector and the Trade Unions. As for the National Gender Policy, the Ministry of Women will take the lead to promote the empowerment of women. | Regular TRAC 300 Other CS 400 |  |
|  |  |  |  | Sub-Total | 700 |  |
| SL1.7: Civil Society empowerment | Civil society organizations and human resources strengthened in planning and management of development projects and processes in an enabling policy and regulatory environment Indicators: Number of accountability processes documented and verified by a regulatory body by 2007; | - A policy, regulatory and legal framework for NGOs/CBOs formulated - Capacity in accountability processes built for NGOs/CBOs - Capacity of NGOs/CBOs developed in strategic planning as well as formulation, monitoring and evaluation of projects | - A policy, regulatory and legal framework for NGOs/CBOs available by July 2005 (Baseline: nil) - 15% of NGOs/CBOs following established accountability procedures by end 2007 (Baseline: not documented) - 30% of NGOs/CBOs staff trained in strategic planning, formulation, monitoring and evaluation of projects (Baseline: no exact studies available, but MACOSS has had several training workshops) | The Mauritius Council of Social Services (MACOSS), an NGO umbrella organization, will lead the process in the three strategic outcomes, in collaboration with the Ministry of Social Security and the UNDP. The EU’s non-state actors programme will be involved. Other donors will be approached for resource mobilization through their small grants programmes. | Regular TRAC 100 Other CS 100 |  |
|  |  |  |  | Sub-Total | 200 |  |
| SL1.8: Making ICTD work for the poor | The development potential and long-run sustainability of ICT Small and Medium-sized Enterprises (SMEs) ensured in an enabling strategic ICT environment; the ICT sector envisioned and developed as an enabler of development providing equal ICT opportunities to citizens Indicators: % Increase in the number, profitability and scale of business of ICT Small and Medium–sized Enterprises (SMEs); % Increase in employment and expertise in ICT sector by 2007 | - An ICT Incubator Appraisal Report, an ICT Incubator Training Plan, an ICT Incubator Marketing and an ICT Incubator Business and Partnership Strategic Plan formulated - Capacity of the ICT Incubator Centre and the ICT incubators built in management, marketing, business and networking strategies and international best practices applied - National ICT Strategy and Action Plan formulated | - An ICT Incubator Appraisal Report, an ICT Incubator Training Plan, an ICT Incubator Marketing and an ICT Incubator Business and Partnership Strategic Plan available by March 2005 (Baseline: not yet available) - 30% ICT incubators applying management, marketing, business and networking strategies as per the developed plans by June 2006 (Baseline: nil) - National ICT Strategy and Action Plan available by March 2006 (Baseline: ICT Strategy of 1998-2005 has become obsolete) | The National Computer Board (NCB), including the ICT Incubator Centre will take the leading role to develop an overall plan for ICT incubators in Mauritius, with the financial and technical support of UNDP. As for output 2, a joint collaboration will be sought with the World Bank under its Information for Development Program (InfoDev) for the capacity building of the ICT incubators and the ICT Incubator Centre. The Ministry of Information Technology and Telecommunications (MITT) jointly with the Prime Minister’s Office will take a leadership role, in collaboration with all important national ICT strategic partners such the NCB, the Information and Communications Technical Authority (ICTA) and the CSO/private sector to develop a National ICT Strategy. The Ministry of Foreign Affairs, International Trade and Regional Cooperation will ensure that the ICT Strategy and Action Plan are an essential part of Mauritius’s position in relevant bilateral, regional and multilateral trade negotiations. | Regular TRAC 200 Other CS 200 |  |
|  |  |  |  | Sub-Total | 400 |  |
| SL2.7: Public administration reform and anti-corruption | An effective and efficient anti-corruption body in operation and increased public awareness of ethics and good governance principles Indicators: Number of best practices shared; Number of exchange with comparable country situations | - Capacity built of the Independent Commission against Corruption (ICAC) through system enhancement and community support through public education in line with international best practices - Capacity built of the Media in investigative journalism | - ICAC’s systems enhanced by February 2006 and public education (re. community support) activities finalized by December 2005 (Baseline: no data available yet as ICAC is a recently established institution) - Workshop on investigative journalism held by December 2005 (baseline: one workshop held sponsored by UNDP in 1998) | The Independent Commission against Corruption (ICAC) will take the lead role and will enter into partnerships through South-South cooperation with other anti-corruption institutions. An intervention platform will be set up with the Media to build alliances against corruption in the country. The UNDP and other UN Agencies will provide technical expertise and access to international best practices. | Regular TRAC 100 Other CS 150 |  |
|  |  |  |  | Sub-Total | 250 |  |
| Objective 2 : | Promotion and protection of the environment and energy. |  |  |  |  |  |
| Goal 3: Energy and environment for sustainable development |  |  |  |  |  |  |
| SL1: Frameworks and strategies for sustainable development | Improvement of capacities of local authorities, CSOs, private and public sectors with the selection of the most environmentally sound options for management and disposal of hazardous substances in Mauritius and Rodrigues Indicator: A set of feasible options for the most appropriate, economical and BET option available by 2007 | - Enabling policy, institutional and legislative environment reviewed. - Sustainability, financial and risk assessment studies completed. - Coordination mechanism designed and put in place. - National Strategy for the management and disposal of hazardous substances formulated | - Review of the policy, institutional and legislative environment available by June 2005 (Baseline: nil) - Sustainability, financial and risk assessment studies available by March 2006 (Baseline: nil) - Coordination mechanism designed and put in place by March 2007 Baseline: nil) - National Strategy for the management and disposal of hazardous substances available by December 2007 (Baseline: nil) | The Ministry of Environment and the Ministry of Local Government will jointly take the leadership role in the review and establishment of a strategy for the management and the disposal of hazardous substances. UNDP will support the process, and also contribute to the consultations that will be held with the private sector and the civil society in order to set up the coordination mechanisms. Based on cost-benefit and other market-based analyses, private sector companies will contribute to the identification of potential options for the management of hazardous substances. | Regular TRAC 27 Other CS 75 |  |
|  |  |  |  | Sub-Total | 102 |  |
| SL 3: Access to sustainable energy services. | Improved national capacity to implement global environment commitment (reduction in GHG emissions from non renewable fossil fuel) through energy efficiency and energy conservation in buildings in Mauritius. Indicator: 30% Increase in energy audits and energy conservation activities in the various sectors (industries, hotel, etc) by 2007 | - Establishment of a national legislative and institutional framework, introduction of norms and standards, fiscal incentives following the completion of a financial review. - Energy efficient tools developed and incorporated in buildings designs and construction through revised legislations and code of practice. - Public and private sectors, CSOs and CBOs sensitized with regards to energy conservation and sound practices and networked through a national consultative Forum on energy efficiency and energy conservation | - Financial review approved by mid 2006. Legislative and institutional framework established, introduction of norms and standards and fiscal incentives by and beyond end 2007 (Baseline: nil) - Legislations revised and code of practice available by end 2006. Tools developed beyond 2007. (Baseline: nil). - National consultative Forum on energy efficiency and energy conservation held by mid 2006. Public and private sectors, CSOs and CBOs sensitized and networked by mid 2007 (Baseline: nil) | The Ministry of Public Utilities will take the leadership role throughout the formulation and implementation process. Other stakeholders such as the Ministry of Environment and other ministries, the Central Electricity Board, the Central Statistical Office, the Mauritius Research Council, the University of Mauritius, the National Housing Development Cooperation and various others will provide their in-kind contribution by participating in the consultative processes. These institutions will also co-develop energy efficient tools. The private sector, namely the building developers and the Association des Hoteliers et Restaurateurs de l’ Ile Maurice (AHRIM) will provide, inter alia, a market-based perspective to the elaboration of the new code of practice. UNDP will provide technical and financial inputs throughout the whole stage. | Regular TRAC Other CS 700 GEF 700 |  |
|  |  |  |  | Sub-Total | 1400 |  |
| SL 4: Sustainable land management to combat desertification and land degradation | Improved national capacity to implement global environment commitment through capacity building for a sustainable land management in Mauritius and Rodrigues Indicator: a set of policy and planning tools available by 2006 and, in the context of NAP, priority projects identified and budgeted | - Capacity of national stakeholders enhanced with regard to SLM - NAP and NFAP formulated and NAP submitted to UNCCD Secretariat - A set of policy and planning tools developed and strengthened - LIMS established and SLM integrated in local development plans and implemented - Legislative framework and financial mechanisms set up to promote partnerships for forest and ESAs land management under private sector ownership | - SLM capacity-building activities for stakeholders done by end 2005 (Baseline: nil) - NAP and NFAP formulated and submitted to UNCCD Secretariat by mid 2006 (Baseline: nil) - A set of policy and planning tools developed and strengthened by end 2006 (Baseline: nil) - LIMS established and SLM integrated in local development plans and implemented by and beyond end 2007 (Baseline: nil) - Legislative framework and financial mechanisms set up by and beyond end 2007 (Baseline: nil) | The Forestry Service of the Ministry of Agriculture, Food Technology and Natural Resources will lead the process, in collaboration with the Ministry of Housing and Lands and the Rodrigues Regional Assembly (Rodrigues Island) throughout all stages of project formulation and implementation. Privately owned forest landowners, hotel industry and other private sector actors will provide their inputs in relation to the protection of environment sensitive areas (ESAs). Many other partners within the public, the private sector and the civil society will be involved as land use is highly multi-sectoral. UNDP, including DDC and FAO, as well as the Global Mechanism and the Secretariat of the UNCCD could provide technical and financial inputs. The financial support from bilateral donors such as CIDA will also be explored. | Regular TRAC Other CS 600 GEF 600 |  |
|  |  |  |  | Sub-Total | 1200 |  |
| SL 5: Conservation and Sustainable use of biodiversity | Improve national capacity in partnerships for sustainable co-management of MPAs initially developed and tested through a demonstration site in Rodrigues and replicated within Mauritius and Rodrigues Indicator: one fully co-managed MPA in Rodrigues by 2007 and replication of the co-managed approach to other MPAs in Mauritius initiated | - Capacity building at the site and national level for all stakeholders carried out, sensitization and dissemination of results - Tools for sustainable MPAs co-management developed and tested at pilot site, sustainable practices promoted. Integrated Management Plan developed and implemented - Coordination mechanisms established. - MPAs co- management results integrated into national policies and legislations | - Capacity building activities, sensitization and dissemination of results carried out by end 2007 (Baseline: nil) - Tools developed and tested at pilot site and sustainable practices promoted by end 2007. Integrated Management Plan developed and implemented by end 2007 (Baseline: nil) - Coordination mechanisms established by end 2007 (Baseline: nil) - MPAs co-management results integrated into national policies and legislations by and beyond 2007 (Baseline: nil) | The Ministry of Fisheries in joint collaboration with the Executive Council of the Rodrigues Regional Assembly will take the leadership role throughout all stages of the project execution. The Albion Fisheries Research Centre will be supporting the Ministry of Fisheries to develop an enabling policy and institutional framework for MPAs at national level (objective 1), whereas the RRA will be essential in leading the identification and testing of MPA co-management practice at the demonstration site in Rodrigues (objective 2). There will be an involvement of the players at the demonstration site and lessons learnt from this process of collaboration between government, private sector, particularly the local hotels and the Association des Hoteliers et Restaurateurs de l’ Ile Maurice (AHRIM), and local communities will be important in informing the ICZM process at the national level. There will also be extensive participation of a range of government ministries, civil society and private sector actors. UNDP will provide technical and financial inputs. | Regular TRAC Other CS 540 GEF 700 |  |
|  |  |  |  | Sub-Total | 1240 |  |
|  |  |  |  | Totals | Regular TRAC 1.1.1 1,027 Other CS 3,165 GEF 2,000 Overall 6,192 |  |

Annex II: Resource mobilisation targets table for Mauritius

2005-2007

(In thousands of United States dollars)

| Source | Amount | Comments |
| --- | --- | --- |
| UNDP REGULAR RESOURCES |  |  |
| Estimated carry-over | (23) | Includes carry-over of TRAC 1, TRAC 2 and the earlier AOS allocations. |
| TRAC 1.1.1 | 1,050 | Assigned immediately to country. |
| TRAC 1.1.2 | 66.7 per cent of TRAC 1.1.1 | This range of percentages is presented for initial planning purposes only. The actual assignment will depend on the availability of high-quality programmes. Any increase in the range of percentages would also be subject to availability of resources. |
| TRAC 1.1.3 |  |  |
| SPPD/STS |  |  |
| Subtotal | 1,027a/ |  |
| UNDP OTHER RESOURCES |  |  |
| Government cost-sharing, including Government Cash Contribution | 3,165 |  |
| Third-party cost-sharing |  |  |
| Funds, trust funds and other Of which: GEF | 2,000 |  |
| Subtotal | 5,165 |  |
| GRAND TOTAL | 6,192 a/ |  |

a/  Not inclusive of TRAC 1.1.2, which is allocated regionally for subsequent country application. Abbreviations:  TRAC = target for resource assignment from the core; SPPD = support for policy and programme development; STS = support for technical services; UNCDF = United Nations Capital Development Fund; UNV = United Nations Volunteers; GEF = Global Environment Facility

Annex III: Glossary

AGOA: Africa Growth and Opportunity Act

AfDB: African Development Bank

BET: Best Environmental Technology

CBO: Community-Based Organization

CCA: Common Country Assessment

CIDA: Canadian International Development Agency

CSO: Civil Society Organizations

CPD: Country Programme Document

DDC: Drylands Development Centre

DFID: Department for International Development (UK)

ESA: Environmentally Sensitive Area

EPMU: Economic Planning and Monitoring Unit

EU: European Union

FAO: Food and Agricultural Organization

FDI: Foreign Direct Investment

GCS: Government Cost-Sharing

GEF: Global Environment Facility

GEF/SGP: Global Environment Facility Small Grants Programme

GHG: Green House Gas

GRB: Gender-Responsive Budgeting

ICAC: Independent Commission against Corruption

ICT: Information and Communications Technology

ICTA: Information and Communications Technology Authority

ICZM: Integrated Coastal Zone Management

IFAD: International Fund for Agricultural Development

ILO: International Labour Organization

IT: Information Technology

LIMS: Land Information Management Systems

MDG: Millennium Development Goals

MPA: Marine Protected Areas

MYFF: Multi-Year Funding Framework

NAP: National Action Programme

NCB: National Computer Board

NEPAD: New Partnership for Africa’s Development

NEX: National Execution

NGO: Non-Governmental Organization

NFAP: National Forestry Action Plan

POPs: Persistent Organic Pollutants

RBM: Results-Based Management

RRA: Rodrigues Regional Assembly

SIDS: Small Island Developing States

SL: Service Line

SLM: Sustainable Land Management

SME: Small and Medium Enterprise

SURF: Sub-regional Resource Facility

TRAC: Target Resources Allocated from the Core

UN: United Nations

UNCCD: United Nations Convention to Combat Desertification

UNDAF: United Nations Development Assistance Framework

UNICEF: United Nations Children’s Fund

UNIFEM: United Nations Development Fund for Women

UNISTAR: United Nations International Short-Term Advisory Resources

UNV: United Nations Volunteers

WB: World Bank

WHO: World Health Organization

(http://un.intnet.mu/UNDP/html/pub.htm, http://economicdevelopment.gov.mu/pov.htm, (http://mof.gov.mu/index2.htm, http://women.gov.mu/gender_bureau.htm)